## Work Plan
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Epics | Original Estimate | Updated Estimate | Priority | Allocated Team | Team Days (current 25SP/d) | Team Days (Uplifted 30SP/d) | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | Total
Estimate Build – Carbon (incl. EPD) | Venkatesh& Minas |  | 2025-12-24 | [5 empty] | VER10-8954, VER10-9428, VER10-9464, VER10-9527, VER10-9523 | 575 | 495 |  | 2 x Teams | 70.7143 | 30.9375 | [73 empty] | 0
Carbon Resource Library | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 55 | 1 | Team 1 | 8 | 7 | [7 empty] | X |  |  | X | X | X | X | X |  |  | X | F | [54 empty] | 7
Carbon Item Library | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 85 | 2 | Team 4 | 12.4286 | 10.875 | [7 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [48 empty] | 11
WBS Carbon & Calc | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 75 | 4 | Team 4 | 11.2857 | 9.875 | [24 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [34 empty] | 10
Baseline Assumption | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 40 | 3 | Team 1 | 6.1429 | 5.375 | [19 empty] | X | X | X |  |  | X | X | F | [46 empty] | 5
EPD | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 75 | 5 | Team 1 | 11.4286 | 10 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | F | [31 empty] | 10
Cost to Carbon Library | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 85 | 7 | Team 1 | 13.1429 | 11.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [12 empty] | 12
Auto-Allocate | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 40 | 6 | Team 4 | 6.5714 | 5.75 | [39 empty] | X | X | X | X |  |  | X | X | F | [25 empty] | 6
Carbon Reports | MInas |  | ? | 2026-01-09 | [6 empty] | 40 |  | Team 3 | 5.7143 | 5 | [52 empty] | X | X | X | X | X |  |  | F | [13 empty] | 5
Interim Forecasting Tool (incl EPD) | Venkatesh |  | 2026-01-09 | 2026-01-13 | 2026-01-21 | N/A | 2026-01-28 | 2026-01-28 | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 | 1 | Team 4 | 28.7143 | 25.125 | X |  |  | X | X | X | X | [32 empty] | X | X | X | X | X |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [9 empty] | 24
Long-Term Appraisal | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8565 | 260 | 180 | 4 | Team 2 | 26.2857 | 11.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [12 empty] | 12
Comparator | Funsho | Y | 19/12/2025 (Done on time) | 2025-12-24 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8953 | 120 | 120 | 4 | Team 5 | 17.7143 | 15.5 | [38 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [12 empty] | 16
Workflow | Funsho | Y | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9028 | 35 | 35 | 5 | Team 3 | 5.7143 | 5 |  |  |  | X | X | X | X | X |  |  | F | [62 empty] | 5
Tasks | Funsho |  | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9027 | 40 | 0 |  | N/A | 0 | 0 | [73 empty] | 0
Portfolio/Programme Risk | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-22 | N/A | 2026-01-29 | 2026-01-29 | VER10-9494 | 80 | 60 | 5 | Team 3 | 9.2857 | 8.125 | [38 empty] | X | X | X | X | X |  |  | X | X | X | F | [24 empty] | 8
[14 empty] | 0 | 0 | [73 empty] | 0
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 (Done on time) | 2025-12-24 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | No Epic | 20 | 20 | 6 | Team 5 | 3.7143 | 3.25 |  |  |  | X | X | X | [67 empty] | 3
Scenario Analysis (Chapter 7) | Venkatesh? (TBC) |  | Fri, 13 Feb 2026 | Fri, 20 Feb 2026 | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | VER10-8958 | 140 | 100 | 5 | Team 5 | 15 | 13.125 | [24 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  |  | X | X | X | [31 empty] | 13
Star Rates | Minas? (TBC) |  | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-13 | 2026-02-13 | No Epic | 90 | 60 |  | Team 2 | 8.5714 | 7.5 | [10 empty] | X | X | X | X | X |  |  | X | X | X | F | [52 empty] | 8
TPE | Venkatesh |  | 2026-01-23 | 2026-01-28 | 2026-02-06 | N/A | 2026-02-13 | 2026-02-13 | VER10-9184 | 350 | 215 | 4 | Team 4 | 31.2857 | 27.375 | [73 empty] | 0
Dashboards (Power BI) | Minas |  | Fri, 16 Jan 2026 (Original 24/12/2025) | Wed, 21 Jan 2026 (Original 31/12/2025) | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | No Epic | 40 | 40 | 2 | Dashboard Team | 6 | 5.25 | [38 empty] | X | X | X | X | X |  |  | X | F | [26 empty] | 6
Contractor Fee Library | Minas |  | 2026-01-09 | 2026-01-14 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | VER10-9271 | 90 | 80 | 3 | Team 2 | 11.8571 | 10.375 | [20 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | F | [38 empty] | 10
System Access | Minas |  | 2026-01-16 | N/A | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | No Epic | 40 | 40 | 3 | Team 5 | 6.1429 | 5.375 | [73 empty] | 0
Audit Log | Minas |  | 2026-01-30 | 2026-02-06 | N/A | 2026-02-13 | ? |  | VER10-8955 | 10 | 11 |  | Team 5 | 1.5714 | 1.375 | [73 empty] | 0
WBS Tags and Custom Fields | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8916, VER10-8268 | Need Estimate | Need Estimate |  | Team 3 | 0 | 0 | [73 empty] | 0
Reporting Foundation Admin | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8476 | 19 | 19 |  | Team 3 | 2.7143 | 2.375 | [10 empty] | X | X | F | [60 empty] | 2
Inflation | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8903, VER10-8570 | 41 | 41 |  | Team 2 | 5.8571 | 5.125 | [34 empty] | X | X |  |  | X | X | X | X | F | [30 empty] | 6
[14 empty] | 0 | 0 | [73 empty] | 0
AR and O&M fixed reports |  |  | Done | Done | Done | Done | Done | Done | VER10-7878, VER10-7879 | 47 | 47 |  | Team 3 | 6.7143 | 5.875 | [24 empty] | X | X | X | X | X |  |  | X | F | [40 empty] | 6
CCESS |  |  | Done | Done | Done | Done | Done | Done | VER10-6966 | 5 | 5 |  | Team 3 | 0.71429 | 0.625 | [32 empty] | X | F | [39 empty] | 1
[10 empty] | 2179 | 1768 | 2333 |  | 333.2857 | 249.1875 | 1 | 0 | 0 | 3 | 3 | 3 | 2 | 3 | 0 | 0 | 4 | 4 | 3 | 3 | 3 | 0 | 0 | 3 | 2 | 3 | 3 | 3 | 0 | 0 | 5 | 5 | 4 | 5 | 5 | 0 | 0 | 5 | 5 | 4 | 4 | 4 | 0 | 0 | 5 | 8 | 8 | 7 | 7 | 1 | 0 | 7 | 6 | 5 | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186
Note on B3: Minas Kamel: Funsho's: - Auto Allocate - Carbon Reporting
Note on C20: Minas Kamel: Richard?

## Capacity
|  | per week | whole team
Required per team per day | 7 | 35 | 175
Ideal per team per day | 8 | 40 | 200
per dev per day |  | 1.4286

## Work Plan - Review SP (WIP)
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Epics | Story Point Estimate for Dev |  | Assumed Estimate | Team Days (current 25SP/d)
Estimate Build – Carbon | Venkatesh & Funsho |  | 2025-12-24 | 2025-12-30 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 | VER10-8954, VER10-9428, VER10-9464, VER10-9527, VER10-9523 | 575 | 414 |  | 141.2857
Interim Forecasting Tool | Venkatesh |  | 2026-01-09 | 2026-01-13 | 2026-01-21 | N/A | 2026-01-28 | 2026-01-28 | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 |  | 53.8571
Long-Term Appraisal | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8565 | 260 | 200 |  | 65.7143
Comparator | Funsho | Y | 19/12/2025 (Done on time) | 2025-12-24 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8953 | 120 | 100 |  | 31.4286
Workflow | Funsho | Y | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9028 | 35 | 35 |  | 10
Tasks | Funsho |  | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9027 | 40 | 0 |  | 5.7143
Portfolio/Programme Risk | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-22 | N/A | 2026-01-29 | 2026-01-29 | VER10-9494 | 80 | 60 |  | 20
0
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 (Done on time) | 2025-12-24 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | No Epic | 20 | 20 |  | 5.7143
Scenario Analysis (Chapter 7) | Venkatesh? (TBC) |  | Fri, 13 Feb 2026 | Fri, 20 Feb 2026 | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | VER10-8958 | 140 | 100 |  | 34.2857
Star Rates | Minas? (TBC) |  | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-13 | 2026-02-13 | No Epic | 90 | 60 |  | 21.4286
TPE | Venkatesh |  | 2026-01-23 | 2026-01-28 | 2026-02-06 | N/A | 2026-02-13 | 2026-02-13 | VER10-9184 | 350 | 215 |  | 80.7143
Dashboards (Power BI) | Minas |  | 2025-12-24 | 2025-12-31 | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | No Epic | 40 | 40 |  | 11.4286
Contractor Fee Library | Minas |  | 2026-01-09 | 2026-01-14 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | VER10-9271 | 90 | 80 |  | 24.2857
System Access | Minas |  | 2026-01-16 | N/A | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | No Epic | 40 | 40 |  | 11.4286
Audit Log | Minas |  | 2026-01-30 | 2026-02-06 | N/A | 2026-02-13 | ? |  | VER10-8955 | 10 | 11 |  | 3
WBS Tags and Custom Fields | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8916, VER10-8268 | Need Estimate | Need Estimate |  | 0
Reporting Foundation Admin | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8476 | 19 | 19 |  | 5.4286
Inflation | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8903, VER10-8570 | 41 | 41 |  | 11.7143
0
AR and O&M fixed reports |  |  | Done | Done | Done | Done | Done | Done | VER10-7878, VER10-7879 | 47 | 47 |  | 13.4286
CCESS |  |  | Done | Done | Done | Done | Done | Done | VER10-6966 | 5 | 5 |  | 1.4286
[10 empty] | 2179 | 1687 |  | 552.2857
Formulas:
SA (Technical Solution Design) = [VIGO: UI/UX Design]+7
SA (Technical Solution Design) = [Internal: UI/UX Design]+7
All Design Activities Due Date = [SA (Technical Solution Design)]

## Teams Allocation
| # points / week | 2025-12-22 | 2025-12-29 | 2025-01-05 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23
Team 1 Venkatesh & Sunjeet (3 devs) | 25 | [12 empty] | Regression/UAT | UAT
Team 2 Minas & Manish (3 devs) | 25
Team 3 Minas & Vivek (2 devs) | 20
Team 4 Venkatesh & Amit (4 devs) | 30
Team 5 Minas & Laurence (2 devs) | 25
TOTAL | 125
To deliver 1500 points (weeks) | 12
To deliver 1500 points in 9 weeks (SP per week) | 166.6667
Team | Epic | Reduced Estimate | # weeks | Dependent On | Extra Weeks
Team 1 Venkatesh & Sunjeet | Carbon (incl EPD, Auto Allocate) | 455 | 18.2 |  | 6.2
| Carbon Resource Library | 55 | 2.2
| Carbon Item Library | 85 | 3.4 | Carbon Resource
| WBS Carbon & Calc | 75 | 3 | Carbon Libraries
| Baseline Assumption | 40 | 1.6
| EPD | 75 | 3
| Cost to Carbon Library | 85 | 3.4 | Carbon WBS
| Auto-Allocate | 40 | 1.6 | Carbon Libraries
| Carbon Reports | - | -
Team 2 Minas & Manish | Inflation | 41 | 1.64 |  | 2.44
| LTA | 180 | 7.2 | Carbon WBS
| Star Rates | 60 | 2.4
| Contractor Fee Library | 80 | 3.2 | IFT?
Team 3 Minas & Vivek | Reporting Foundation Admin | 19 | 0.95 |  | -1.7
| Portfolio/Programme Risk | 60 | 3
| AR and O&M fixed reports | 47 | 2.35 | Carbon & Reporting Foundation Admin
| CCESS | 5 | 0.25 | Carbon & Reporting Foundation Admin
| Carbon Reports | 40 | 2 | Carbon
| Workflow | 35 | 1.75
Team 4 Venkatesh & Amit | Supply Chain - Interim Forecasting Tool | 200 | 6.6667 | Carbon WBS | 1.8333
| TPE | 215 | 7.1667
Team 5 Minas & Laurence | Audit Log | 11 | 0.44 |  | -0.36
| System Access | 40 | 1.6
| Calculators/Cost Models | 20 | 0.8
| Comparator | 120 | 4.8 | Carbon WBS
| Scenario Analysis | 100 | 4 | Comparator
Work Streams |  | Reduced Estimate | Team
Dashboards (Power BI) |  | 40 | Jonny?
WBS Tags and Custom Fields |  | Need Estimate | ?
Note on C1: Minas Kamel: Assumption: Teams do 25 points a day
Note on C12: Minas Kamel: Funsho's: - Auto Allocate - Carbon Reporting

## MVP Meetings
Topic | Owner | Meeting (UK timezone) | Meeting (AU timezone) | Notes
EPD/Cost to Carbon Factor | Venkatesh | Tue 23rd Dec 10PM-11PM | Wed 24th Dec 9AM-10AM | Meeting done
LTA | Minas | Wed 24th Dec 8AM-9:30AM | Wed24th Dec 7PM-8:30PM | Meeting done
TPE & Auto Allocate (Cost & Carbon) | Venkatesh | Sun 28th Dec 10PM-11:30PM | Mon 29th Dec 9AM-10:30AM | Meeting done
Scenario Analysis (Chapter 7) | Minas | Mon 29th Dec 7AM-8:30AM | Mon 29th Dec 6PM-7:30PM
Carbon Reports | Minas
Supply Chain - Interim Forecasting Tool (incl EPD) | Venkatesh | N/A | N/A | Venkatesh needs meeting with NH
Dashboards (Power BI) | Minas
Comparator | Minas
Workflow | Minas
Tasks | Minas
Calculators/Cost Models (Chapter 10) | Minas
Star Rates | Minas
Contractor Fee Library | Minas
|  | UK | AU | Status | Topic
Mark's avail. |  | Wed 24th Dec UK morning | Wed 24th AU evening | Taken | LTA
|  | Sat 27th Dec 7AM-9AM | Sat 27th Dec 6PM-8PM | X
|  | Sun 28th Dec 7AM-9AM | Sun 28th Dec 6PM-8PM | X
|  | Sun 28th Dec 10PM-11:30PM | Mon 29th Dec 9AM-10:30AM | Taken | TPE & Auto Allocate (Cost & Carbon)
|  | Mon 29th Dec 7AM-9AM | Mon 29th Dec 6PM-8PM | Taken | Scenario Analysis (Chapter 7)
|  | Mon 29th Dec 10PM-11:30PM | Tue 30th Dec 9AM-10:30AM | After MVP deadline (Mon 29th)
|  | Fri 2nd Jan UK morning | Fri 2nd Jan AU evening | After MVP deadline (Mon 29th)

## Work Plan V2
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Dev Start | Dev Finish | SG1 | SG2 | SG3 | SG4 | SG5 | SG6 | SG7 | SG8 | SG9 | SG10 | Epics | Original Estimate | Updated Estimate | Priority | Allocated Team | Team Work Days (7 SP pd) | Team Work Days (8 SP pd) | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | Total
Carbon Resource Library | Venkatesh |  | 2025-12-24 | 2026-01-07 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-16 |  |  | √ |  | √ | [8 empty] | 575 | 55 | 1 | Team 1 | 7.8571 | 6.875 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | F | [66 empty] | 7
Carbon Item Library | Venkatesh |  | 2025-12-24 | 2026-01-07 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-16 |  |  | √ |  | √ | [9 empty] | 85 | 2 | Team 4 | 12.1429 | 10.625 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [60 empty] | 11
WBS Carbon & Calc | Venkatesh |  | 2025-12-24 | 2026-01-09 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 |  |  | √ | [11 empty] | 75 | 4 | Team 4 | 10.7143 | 9.375 | [31 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [46 empty] | 10
Baseline Assumption | Venkatesh |  | 2025-12-24 | 2026-01-09 | 2026-01-16 | N/A | 2026-01-21 | 2026-01-21 |  |  | √ | [11 empty] | 40 | 3 | Team 1 | 5.7143 | 5 | [25 empty] | X | X | X | X |  |  | X | F | [59 empty] | 5
EPD | Venkatesh |  | 2025-12-24 | 2026-01-09 | 2026-01-23 | N/A | 2026-01-29 | 2026-01-29 |  |  | √ | [11 empty] | 75 | 5 | Team 1 | 10.7143 | 9.375 | [32 empty] | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | F | [44 empty] | 11
Cost to Carbon Library | Venkatesh |  | 2025-12-24 | 2026-01-16 | 2026-01-23 | N/A | 2026-01-30 | 2026-01-30 |  |  | √ | [11 empty] | 85 | 7 | Team 1 | 12.1429 | 10.625 | [47 empty] | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [28 empty] | 12
Auto-Allocate | Venkatesh |  | 2025-12-24 | 2026-01-16 | 2026-01-23 | N/A | 2026-01-30 | 2026-01-30 |  |  | √ | [11 empty] | 40 | 6 | Team 4 | 5.7143 | 5 | [45 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 10
Carbon Reports | Minas |  | 2026-01-16 | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-06 | [14 empty] | 40 |  | Team 3 | 5.7143 | 5 | [41 empty] | X | X |  |  | X | X | X | F | [43 empty] | 5
Interim Forecasting Tool (incl EPD) | Venkatesh |  | 2026-01-09 | 2026-01-15 | 2026-01-22 | N/A | 2026-01-29 | 2026-01-29 | [12 empty] | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 | 1 | Team 4 | 28.5714 | 25 |  |  |  | X | X | X | X | X |  |  | X | X | X | X | [45 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | F | [9 empty] | 26
Long-Term Appraisal | Minas |  | Fri 12 Dec 2025 | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-06 |  |  | √ | [9 empty] | VER10-9697, VER10-9698, VER10-9699, VER10-9700, VER10-9701, VER10-9702 | 260 | 180 | 4 | Team 2 | 25.7143 | 22.5 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [28 empty] | 26
Comparator | Minas | Y | Fri 12 Dec 2025 | 2026-01-19 | 2026-01-26 | N/A | 2026-02-02 | 2026-02-02 |  |  | √ | [9 empty] | VER10-8953 | 120 | 120 | 4 | Team 5 | 17.1429 | 15 | [31 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [39 empty] | 15
Workflow | Minas | Y | Wed 17 Dec 2025 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 |  |  | √ | [9 empty] | VER10-9028 | 35 | 35 | 5 | Team 3 | 5 | 4.375 | [18 empty] | X | X | X | X |  |  | X | F | [66 empty] | 5
Portfolio/Programme Risk | Minas |  | Fri 12 Dec 2025 | 2026-01-19 | 2026-01-26 | N/A | 2026-02-02 | 2026-02-02 |  |  | √ | [9 empty] | VER10-9494 | 80 | 60 | 5 | Team 3 | 8.5714 | 7.5 | [31 empty] | X | X | X | X | X |  |  | X | X | X | F | [50 empty] | 8
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 |  |  | √ | [9 empty] | No Epic | 20 | 20 | 6 | Team 5 | 2.8571 | 2.5 | [24 empty] | X | X | X | F | [64 empty] | 3
Scenario Analysis (Chapter 7) | Minas? (TBC) |  | 2026-01-23 | 2026-01-30 | 2026-02-06 | N/A | 2026-02-13 | 2026-02-13 | [12 empty] | VER10-8958 | 140 | 100 | 5 | Team 3 | 14.2857 | 12.5 | [52 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  |  | X | X | X | F | [21 empty] | 13
Star Rates | Minas? (TBC) |  | 2026-02-06 | 2026-02-11 | N/A | 2026-02-13 | 2026-02-20 | 2026-02-20 | [12 empty] | No Epic | 90 | 60 |  | Team 2 | 8.5714 | 7.5 | [17 empty] | X | X | X | X | X |  |  | X | X | X | F | [64 empty] | 8
TPE | Venkatesh |  | 2026-01-30 | 2026-02-06 | 2026-02-13 | N/A | 2026-02-20 | 2026-02-20 | [12 empty] | VER10-9184 | 350 | 215 | 4 | Team 5 | 30.7143 | 26.875 | [52 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [10 empty] | 21
Dashboards (Power BI) | Minas |  | 2026-01-09 | 2026-01-16 | N/A | N/A | N/A | N/A | [12 empty] | No Epic | 40 | 40 | 2 | Dashboard Team | 5.7143 | 5 | [17 empty] | X | X | X | X | X |  |  | F | [67 empty] | 5
Contractor Fee Library | Minas |  | 2026-01-30 | 2026-02-04 | N/A | 2026-02-11 | 2026-02-18 | 2026-02-18 | [12 empty] | VER10-9271 | 90 | 80 | 3 | Team 2 | 11.4286 | 10 | [63 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [14 empty] | 10
System Access | Minas |  | 2026-02-06 | N/A | N/A | 2026-02-13 | 2026-02-20 | 2026-02-20 | [12 empty] | VER10-8452 | 40 | 40 | 3 | Team 5 | 5.7143 | 5 |  |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [74 empty] | 10
Audit Log | Minas |  | 2026-01-09 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 | 2026-01-23 | [12 empty] | VER10-8955, VER10-6972 | 10 | 11 |  | Team 5 | 1.5714 | 1.375 | [20 empty] | X | F | [70 empty] | 1
WBS Tags and Custom Fields | Minas |  | Done | Done | Done | Done | Done | Done |  |  | √ | √ | √ | √ | √ | √ |  |  |  |  | VER10-8916, VER10-8268 | 10 | 10 |  | Team 2 | 1.4286 | 1.25 | [6 empty] | X | F | [84 empty] | 1
Reporting Foundation Admin | Minas |  | Done | Done | Done | Done | Done | Done |  |  | √ | √ | √ | √ | √ | √ |  |  |  |  | VER10-8476 | 19 | 19 |  | Team 3 | 2.7143 | 2.375 |  |  |  |  | X | X | X | F | [84 empty] | 3
Inflation | Minas |  | Done | Done | Done | Done | Done | Done |  |  | √ | √ | √ | √ | √ | √ |  |  |  |  | VER10-8903, VER10-8570 | 41 | 41 |  | Team 2 | 5.8571 | 5.125 | [10 empty] | X | X | X | X | X |  |  | F | [74 empty] | 5
AR and O&M fixed reports | Minas |  | Done | Done | Done | Done | Done | Done |  |  | √ | √ | √ | √ | √ | √ |  |  |  |  | VER10-7878, VER10-7879 | 47 | 47 |  | Team 3 | 6.7143 | 5.875 | [7 empty] | X |  |  | X | X | X | X | X |  |  | F | [74 empty] | 6
CCESS | Minas |  | Done | Done | Done | Done | Done | Done |  |  | √ | √ | √ | √ | [6 empty] | VER10-6966 | 5 | 5 |  | Team 3 | 0.71429 | 0.625 | [48 empty] | X | F | [42 empty] | 1
[22 empty] | 2149 | 1778 | 1848 |  | 254 | 222.25 | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 3 | 0 | 0 | 4 | 4 | 4 | 4 | 5 | 0 | 0 | 4 | 5 | 5 | 6 | 5 | 0 | 0 | 5 | 4 | 4 | 3 | 3 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 4 | 0 | 0 | 3 | 4 | 4 | 4 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238
Key | In progress | [23 empty] | Team 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
| Complete | [23 empty] | Team 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
| At risk (Mitigation) | [23 empty] | Team 3 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
| Blocked | [23 empty] | Team 4 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
[25 empty] | Team 5 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
[25 empty] | Total |  |  | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 3 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 2 | 3 | 3 | 4 | 3 | 0 | 0 | 4 | 4 | 4 | 3 | 3 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 4 | 0 | 0 | 3 | 4 | 4 | 4 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C17: Minas Kamel: Richard?

## Stage Gate Tracker
Gate | Owner | Rationale | Pass Criteria (Evidence Required) | Carbon Resource Library | Carbon Item Library | WBS Carbon & Calc | Baseline Assumption | EPD | Cost to Carbon Library | Auto-Allocate | Carbon Reports | Interim Forecasting Tool (incl EPD) | Long-Term Appraisal | Comparator | Workflow | Portfolio/Programme Risk | Calculators/Cost Models (Chapter 10) | Scenario Analysis (Chapter 7) | Star Rates | TPE | Dashboards (Power BI) | Contractor Fee Library | System Access | Audit Log | WBS Tags and Custom Fields | Reporting Foundation Admin | Inflation | AR and O&M fixed reports | CCESS
1. Individual PRDs Drafted | Minas | Ensures scope and requirements are explicit before design and build begin, avoiding downstream rework and ambiguity. | • PRDs drafted for each of the MVP epics | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2026-01-16 | 2026-01-09 | 2025-12-12 | 2025-12-12 | 2025-12-17 | 2025-12-12 | 2025-12-18 | 2026-01-23 | 2026-02-06 | 2026-01-30 | 2026-01-09 | 2026-01-30 | 2026-02-06 | 2026-01-09
|  |  | • Functional requirements prioritised (Must / Should / Deferred) | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2026-01-16 | 2026-01-09 | 2025-12-12 | 2025-12-12 | 2025-12-17 | 2025-12-12 | 2025-12-18 | 2026-01-23 | 2026-02-06 | 2026-01-30 | 2026-01-09 | 2026-01-30 | 2026-02-06 | 2026-01-09
|  |  | • In-scope vs out-of-scope clearly defined | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2026-01-16 | 2026-01-09 | 2025-12-12 | 2025-12-12 | 2025-12-17 | 2025-12-12 | 2025-12-18 | 2026-01-23 | 2026-02-06 | 2026-01-30 | 2026-01-09 | 2026-01-30 | 2026-02-06 | 2026-01-09
|  |  | • Dependencies and assumptions explicitly documented | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2026-01-16 | 2026-01-09 | 2025-12-12 | 2025-12-12 | 2025-12-17 | 2025-12-12 | 2025-12-18 | 2026-01-23 | 2026-02-06 | 2026-01-30 | 2026-01-09 | 2026-01-30 | 2026-02-06 | 2026-01-09
2. PRDs Reviewed & Signed Off (NH) | Richard | Confirms shared understanding and agreement with NH to prevent late scope disputes or rework. | • NH review completed
• Explicit NH sign-off received
• No open scope alignment questions
• Any gaps documented, escalated and resolved
3. UX/UI Designs Completed | Richard (coordination) | Prevents design churn during development and ensures build teams are working from stable designs. | • UX/UI designs completed for all in-scope MVP flows
• Designs reviewed and accepted internally
• Ownership agreed (Vigo vs in-house)
• No critical design work outstanding for sprint execution
4. Solution Architectures (SAs) Drafted | Richard (coordination) | Grounds delivery commitments in technical reality and surfaces assumptions, risks, and trade-offs early. | • SAs drafted for each epic
• Architecture simplified to MVP
• Technical assumptions and risks explicit
• Key trade-offs documented
5. SAs Reviewed & Approved | Jerome | Locks technical feasibility before commitments are made and avoids late architectural rework. | • SAs reviewed and approved
• Risks accepted or mitigated
• No unresolved feasibility questions
• Delivery implications understood by Delivery Manager
6. Sprint Planning by Epic Completed | Richard | Ensures execution commitments are realistic, capacity-aligned, and dependency-aware before development starts. | • Sprint plan complete by epic
• Scope aligned to PRDs, UX/UI, and SAs
• Dependencies explicit
• Capacity and story points validated
7. Sprint Execution Completed | Richard | Confirms committed sprint scope is fully built and integrated before validation. | • All committed stories meet Definition of Done
• Code merged with reviews completed
• No open critical or high-severity defects
• Sprint review completed and recorded
8. QA Testing Completed | Caroline | Validates functional correctness and stability prior to business testing. | • Functional and regression tests executed
• Critical/high defects resolved or accepted
• Test summary report completed
• QA sign-off provided
9. DevOps Deployment to UAT | Jerome | Ensures solution is correctly deployed and stable in the UAT environment. | • Successful deployment to UAT completed
• Environment configuration validated
• Monitoring, logging, and rollback in place
• Release notes shared with UAT stakeholders
10. UAT Completed & Accepted | Caroline | Confirms solution meets business needs and is approved for production readiness. | • UAT scenarios executed for all in-scope flows
• Business acceptance criteria met
• No unresolved critical/high UAT defects
• Formal UAT sign-off received

## Weekly 05-Jan
Day | Deliverable / Task | Owner | Stage Gate | RAG | Escalation Request
Monday | Confirm Engineering Team Allocation | Jerome | No | Done
| Confirm Capacity and Resource Level Mapping | Jerome | No | Done
| Send Plan Dates to Vigo for Designs | Richard | No | Done
| External UAT Sanity Checks (R1D) | Caroline | SG8 - QA Complete | Done
Tuesday | Sprint Planning Session 1 for Release 2A | Richard | SG6 - Sprint Planning | In Prog
| Internal UAT Complete (R1D) | Caroline | SG8 - QA Complete | Done
Wednesday | UAT Handover to NH (Release 1D) | Caroline | SG8 - QA Complete |  | Escalation - P2 defect retested in Regression/Internal UAT but not working in Ext UAT
Thursday | Sprint Planning Session 2 for Release 2A | Richard | SG6 - Sprint Planning
Friday | Audit Log Released | Minas | SG1 - PRD | Done
| PowerBI Dashboards | Minas | SG1 - PRD
| Interim Forecasting Tool | Minas | SG1 - PRD |  | Escalation - meeting needed with NH - set-up for Weds 8am UK time - Go to green after
| Carbon Resource Library | Richard | SG2 - NH Sign-Off
| Carbon Item Library | Richard | SG2 - NH Sign-Off
| WBS Carbon and Calcs | Richard | SG2 - NH Sign-Off
| Baseline Assumption | Richard | SG2 - NH Sign-Off
| Calculators and Cost Models | Richard | SG2 - NH Sign-Off
| Workflow | Richard | SG2 - NH Sign-Off
| EPD | Richard | SG2 - NH Sign-Off
| Carbon Resource Library | Richard | SG3 - UX/UI Design | Done
| Carbon Item Library | Richard | SG3 - UX/UI Design | Done

## Action Log
ID | Action | Owner | Raised Date | Due Date / RAG | Status
A01 | Confirm SharePoint NH Project Artifacts area is live (master tracker R&R recap folder structure) | Richard | 2026-01-05 | 2026-01-06 | Done
A02 | Create separate Stage Gate tracking sheet with criteria-level granularity and target dates | Richard | 2026-01-05 | 2026-01-06 | Done
A03 | Maintain visible daily escalation log carried forward from previous day | Richard | 2026-01-05 | 2026-01-06 | Done
A04 | Fix 3 x P2 defects blocking internal UAT | Jerome | 2026-01-05 | 2026-01-06 | Done
A05 | Complete internal UAT execution and issue UAT documentation to Louise | Caroline | 2026-01-05 | 2026-01-06 | Open
A06 | Finalise onboarding plan for 4 additional engineers chase profiles and shortlist | Jerome | 2026-01-05 | 2026-01-09 | In Prog
A07 | Confirm Vigo resourcing assumptions remain sufficient | Richard / Jerome | 2026-01-05 | 2026-01-07 | In Prog
A08 | Brief John Vigo and book design sessions priority LTA then Comparator | Richard | 2026-01-05 | 2026-01-07 | In Prog
A09 | Re-establish full-team priority alignment session including Vigo | Richard | 2026-01-05 | 2026-01-09 | Done
A10 | Attend NH IFT clarification meeting | Venkatesh | 2026-01-05 | 2026-01-07 08:00 | In Prog
A11 | Post-IFT impact assessment on timeline | Venkatesh / Richard | 2026-01-05 | 2026-01-08 | Open
A12 | Closely monitor NH PRD sign-offs and flag early slippage | Richard | 2026-01-05 | 2026-01-07 | Open