## Work Plan
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Epics | Original Estimate | Updated Estimate | Priority | Allocated Team | Team Days (current 25SP/d) | Team Days (Uplifted 30SP/d) | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | Total
Estimate Build – Carbon (incl. EPD) | Venkatesh & Funsho |  | 2025-12-24 | [5 empty] | VER10-8954, VER10-9428, VER10-9464, VER10-9527, VER10-9523 | 575 | 495 |  | 2 x Teams | 70.7143 | 30.9375 | [73 empty] | 0
Carbon Resource Library | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | [6 empty] | 55 | 1 | Team 1 | 8 | 7 | [7 empty] | X |  |  | X | X | X | X | X |  |  | X | F | [54 empty] | 7
Carbon Item Library | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | [6 empty] | 85 | 2 | Team 4 | 12.4286 | 10.875 | [7 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [48 empty] | 11
WBS Carbon & Calc | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | [6 empty] | 75 | 4 | Team 4 | 11.2857 | 9.875 | [24 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [34 empty] | 10
Baseline Assumption | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | [6 empty] | 40 | 3 | Team 1 | 6.1429 | 5.375 | [19 empty] | X | X | X |  |  | X | X | F | [46 empty] | 5
EPD | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | [6 empty] | 75 | 5 | Team 1 | 11.4286 | 10 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | F | [31 empty] | 10
Cost to Carbon Library | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | [6 empty] | 85 | 7 | Team 1 | 13.1429 | 11.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [12 empty] | 12
Auto-Allocate | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | [6 empty] | 40 | 6 | Team 4 | 6.5714 | 5.75 | [39 empty] | X | X | X | X |  |  | X | X | F | [25 empty] | 6
Carbon Reports | Venkatesh & Funsho |  | ? | 2026-01-09 | [6 empty] | 40 |  | Team 3 | 5.7143 | 5 | [52 empty] | X | X | X | X | X |  |  | F | [13 empty] | 5
Interim Forecasting Tool (incl EPD) | Venkatesh |  | 2026-01-09 | 2026-01-13 | 2026-01-21 | N/A | 2026-01-28 | 2026-01-28 | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 | 1 | Team 4 | 28.7143 | 25.125 | X |  |  | X | X | X | X | [32 empty] | X | X | X | X | X |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [9 empty] | 24
Long-Term Appraisal | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8565 | 260 | 180 | 4 | Team 2 | 26.2857 | 11.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [12 empty] | 12
Comparator | Funsho | Y | 19/12/2025 (Done on time) | 2025-12-24 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8953 | 120 | 120 | 4 | Team 5 | 17.7143 | 15.5 | [38 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [12 empty] | 16
Workflow | Funsho | Y | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9028 | 35 | 35 | 5 | Team 3 | 5.7143 | 5 |  |  |  | X | X | X | X | X |  |  | F | [62 empty] | 5
Tasks | Funsho |  | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9027 | 40 | 0 |  | N/A | 0 | 0 | [73 empty] | 0
Portfolio/Programme Risk | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-22 | N/A | 2026-01-29 | 2026-01-29 | VER10-9494 | 80 | 60 | 5 | Team 3 | 9.2857 | 8.125 | [38 empty] | X | X | X | X | X |  |  | X | X | X | F | [24 empty] | 8
[14 empty] | 0 | 0 | [73 empty] | 0
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 (Done on time) | 2025-12-24 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | No Epic | 20 | 20 | 6 | Team 5 | 3.7143 | 3.25 |  |  |  | X | X | X | [67 empty] | 3
Scenario Analysis (Chapter 7) | Venkatesh? (TBC) |  | Fri, 13 Feb 2026 | Fri, 20 Feb 2026 | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | VER10-8958 | 140 | 100 | 5 | Team 5 | 15 | 13.125 | [24 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  |  | X | X | X | [31 empty] | 13
Star Rates | Minas? (TBC) |  | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-13 | 2026-02-13 | No Epic | 90 | 60 |  | Team 2 | 8.5714 | 7.5 | [10 empty] | X | X | X | X | X |  |  | X | X | X | F | [52 empty] | 8
TPE | Venkatesh |  | 2026-01-23 | 2026-01-28 | 2026-02-06 | N/A | 2026-02-13 | 2026-02-13 | VER10-9184 | 350 | 215 | 4 | Team 4 | 31.2857 | 27.375 | [73 empty] | 0
Dashboards (Power BI) | Minas |  | Fri, 16 Jan 2026 (Original 24/12/2025) | Wed, 21 Jan 2026 (Original 31/12/2025) | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | No Epic | 40 | 40 | 2 | Dashboard Team | 6 | 5.25 | [38 empty] | X | X | X | X | X |  |  | X | F | [26 empty] | 6
Contractor Fee Library | Minas |  | 2026-01-09 | 2026-01-14 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | VER10-9271 | 90 | 80 | 3 | Team 2 | 11.8571 | 10.375 | [20 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | F | [38 empty] | 10
System Access | Minas |  | 2026-01-16 | N/A | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | No Epic | 40 | 40 | 3 | Team 5 | 6.1429 | 5.375 | [73 empty] | 0
Audit Log | Minas |  | 2026-01-30 | 2026-02-06 | N/A | 2026-02-13 | ? |  | VER10-8955 | 10 | 11 |  | Team 5 | 1.5714 | 1.375 | [73 empty] | 0
WBS Tags and Custom Fields | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8916, VER10-8268 | Need Estimate | Need Estimate |  | Team 3 | 0 | 0 | [73 empty] | 0
Reporting Foundation Admin | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8476 | 19 | 19 |  | Team 3 | 2.7143 | 2.375 | [10 empty] | X | X | F | [60 empty] | 2
Inflation | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8903, VER10-8570 | 41 | 41 |  | Team 2 | 5.8571 | 5.125 | [34 empty] | X | X |  |  | X | X | X | X | F | [30 empty] | 6
[14 empty] | 0 | 0 | [73 empty] | 0
AR and O&M fixed reports |  |  | Done | Done | Done | Done | Done | Done | VER10-7878, VER10-7879 | 47 | 47 |  | Team 3 | 6.7143 | 5.875 | [24 empty] | X | X | X | X | X |  |  | X | F | [40 empty] | 6
CCESS |  |  | Done | Done | Done | Done | Done | Done | VER10-6966 | 5 | 5 |  | Team 3 | 0.71429 | 0.625 | [32 empty] | X | F | [39 empty] | 1
[10 empty] | 2179 | 1768 | 2333 |  | 333.2857 | 249.1875 | 1 | 0 | 0 | 3 | 3 | 3 | 2 | 3 | 0 | 0 | 4 | 4 | 3 | 3 | 3 | 0 | 0 | 3 | 2 | 3 | 3 | 3 | 0 | 0 | 5 | 5 | 4 | 5 | 5 | 0 | 0 | 5 | 5 | 4 | 4 | 4 | 0 | 0 | 5 | 8 | 8 | 7 | 7 | 1 | 0 | 7 | 6 | 5 | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186
Note on B3: Minas Kamel: Funsho's: - Auto Allocate - Carbon Reporting
Note on C20: Minas Kamel: Richard?

## Work Plan V2
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Epics | Original Estimate | Updated Estimate | Priority | Allocated Team | Team Work Days (7 SP pd) | Team Work Days (8 SP pd) | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | Total
Carbon Resource Library | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-07 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-16 |  | 575 | 55 | 1 | Team 1 | 8 | 7 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | F | [66 empty] | 7
Carbon Item Library | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-07 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-16 |  |  | 85 | 2 | Team 4 | 12.4286 | 10.875 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [60 empty] | 11
WBS Carbon & Calc | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 |  |  | 75 | 4 | Team 4 | 11.2857 | 9.875 | [31 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [46 empty] | 10
Baseline Assumption | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | 2026-01-16 | N/A | 2026-01-21 | 2026-01-21 |  |  | 40 | 3 | Team 1 | 6.1429 | 5.375 | [25 empty] | X | X | X | X |  |  | X | F | [59 empty] | 5
EPD | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-09 | 2026-01-23 | N/A | 2026-01-29 | 2026-01-29 |  |  | 75 | 5 | Team 1 | 11.4286 | 10 | [32 empty] | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [45 empty] | 10
Cost to Carbon Library | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-16 | 2026-01-23 | N/A | 2026-01-30 | 2026-01-30 |  |  | 85 | 7 | Team 1 | 13.1429 | 11.5 | [47 empty] | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [28 empty] | 12
Auto-Allocate | Venkatesh & Funsho |  | 2025-12-24 | 2026-01-16 | 2026-01-23 | N/A | 2026-01-30 | 2026-01-30 |  |  | 40 | 6 | Team 4 | 6.5714 | 5.75 | [45 empty] | X | X | X | X | X |  |  | X | F | [38 empty] | 6
Carbon Reports | Venkatesh & Funsho |  | 2026-02-02 | 2026-02-09 | 2026-02-16 | N/A | 2026-02-23 | 2026-02-23 |  |  | 40 |  | Team 3 | 5.7143 | 5 | [52 empty] | X | X | X | X | X |  |  | F | [32 empty] | 5
Interim Forecasting Tool (incl EPD) | Venkatesh |  | 2026-01-09 | 2026-01-13 | 2026-01-20 | N/A | 2026-01-27 | 2026-01-27 | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 | 1 | Team 4 | 28.7143 | 25.125 | [53 empty] | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F |  |  |  | 25
Long-Term Appraisal | Funsho |  | Fri 12 Dec 2025 | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-06 | VER10-8565 | 260 | 180 | 4 | Team 2 | 26.2857 | 11.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [31 empty] | 12
Comparator | Funsho | Y | Fri 12 Dec 2025 | 2026-01-19 | 2026-01-26 | N/A | 2026-02-02 | 2026-02-02 | VER10-8953 | 120 | 120 | 4 | Team 5 | 17.7143 | 15.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [28 empty] | 15
Workflow | Funsho | Y | Wed 17 Dec 2025 | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9028 | 35 | 35 | 5 | Team 3 | 5.7143 | 5 |  |  |  | X | X | X | X | X |  |  | F | [81 empty] | 5
Portfolio/Programme Risk | Funsho |  | Fri 12 Dec 2025 | 2026-01-19 | 2026-01-26 | N/A | 2026-02-02 | 2026-02-02 | VER10-9494 | 80 | 60 | 5 | Team 3 | 9.2857 | 8.125 | [38 empty] | X | X | X | X | X |  |  | X | X | X | F | [43 empty] | 8
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 | 2025-12-24 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | No Epic | 20 | 20 | 6 | Team 5 | 3.7143 | 3.25 |  |  |  | X | X | X | F | [85 empty] | 3
Scenario Analysis (Chapter 7) | Venkatesh? (TBC) |  | 2026-01-05 | 2026-01-12 | 2026-01-19 | N/A | 2026-01-26 | 2026-01-26 | VER10-8958 | 140 | 100 | 5 | Team 5 | 15 | 13.125 | [24 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  |  | X | X | X | F | [49 empty] | 13
Star Rates | Minas? (TBC) |  | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-13 | 2026-02-13 | No Epic | 90 | 60 |  | Team 2 | 8.5714 | 7.5 | [10 empty] | X | X | X | X | X |  |  | X | X | X | F | [71 empty] | 8
TPE | Venkatesh |  | 2026-01-19 | 2026-01-26 | 2026-02-02 | N/A | 2026-02-09 | 2026-02-09 | VER10-9184 | 350 | 215 | 4 | Team 1 and 4 | 31.2857 | 13.6875 | [48 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [14 empty] | 21
Dashboards (Power BI) | Minas |  | 2026-01-16 | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-06 | No Epic | 40 | 40 | 2 | Dashboard Team | 6 | 5.25 | [38 empty] | X | X | X | X | X |  |  | F | [46 empty] | 5
Contractor Fee Library | Minas |  | 2026-01-09 | 2026-01-14 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | VER10-9271 | 90 | 80 | 3 | Team 2 | 11.8571 | 10.375 | [20 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | F | [57 empty] | 10
System Access | Minas |  | 2026-01-30 | N/A | N/A | 2026-02-06 | 2026-02-13 | 2026-02-13 | No Epic | 40 | 40 | 3 | Team 5 | 6.1429 | 5.375 | [63 empty] | X |  |  | X | X | X | X | F | [21 empty] | 5
Audit Log | Minas |  | 2026-01-09 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 | 2026-01-23 | VER10-8955 | 10 | 11 |  | Team 5 | 1.5714 | 1.375 | [20 empty] | X | F | [70 empty] | 1
WBS Tags and Custom Fields | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8916, VER10-8268 | Need Estimate | Need Estimate |  | Team 3 | 0 | 0 | [92 empty] | 0
Reporting Foundation Admin | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8476 | 19 | 19 |  | Team 3 | 2.7143 | 2.375 | [10 empty] | X | X | F | [79 empty] | 2
Inflation | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8903, VER10-8570 | 41 | 41 |  | Team 2 | 5.8571 | 5.125 | [34 empty] | X | X |  |  | X | X | X | F | [50 empty] | 5
[14 empty] | 0 | 0 | [92 empty] | 0
AR and O&M fixed reports |  |  | Done | Done | Done | Done | Done | Done | VER10-7878, VER10-7879 | 47 | 47 |  | Team 3 | 6.7143 | 5.875 | [24 empty] | X | X | X | X | X |  |  | X | F | [59 empty] | 6
CCESS |  |  | Done | Done | Done | Done | Done | Done | VER10-6966 | 5 | 5 |  | Team 3 | 0.71429 | 0.625 | [32 empty] | X | F | [58 empty] | 1
[10 empty] | 2139 | 1768 | 1838 |  | 262.5714 | 204.5625 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 3 | 0 | 0 | 3 | 3 | 3 | 4 | 3 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 4 | 4 | 4 | 0 | 0 | 5 | 6 | 6 | 5 | 6 | 0 | 0 | 5 | 4 | 5 | 5 | 5 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 5 | 4 | 4 | 4 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 211
Note on C17: Minas Kamel: Richard?

## Capacity
|  | per week | whole team
Required per team per day | 7 | 35 | 175
Ideal per team per day | 8 | 40 | 200

## Work Plan - Review SP (WIP)
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Epics | Story Point Estimate for Dev |  | Assumed Estimate | Team Days (current 25SP/d)
Estimate Build – Carbon | Venkatesh & Funsho |  | 2025-12-24 | 2025-12-30 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 | VER10-8954, VER10-9428, VER10-9464, VER10-9527, VER10-9523 | 575 | 414 |  | 141.2857
Interim Forecasting Tool | Venkatesh |  | 2026-01-09 | 2026-01-13 | 2026-01-21 | N/A | 2026-01-28 | 2026-01-28 | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 |  | 53.8571
Long-Term Appraisal | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8565 | 260 | 200 |  | 65.7143
Comparator | Funsho | Y | 19/12/2025 (Done on time) | 2025-12-24 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8953 | 120 | 120 |  | 34.2857
Workflow | Funsho | Y | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9028 | 35 | 35 |  | 10
Tasks | Funsho |  | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9027 | 40 | 0 |  | 5.7143
Portfolio/Programme Risk | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-22 | N/A | 2026-01-29 | 2026-01-29 | VER10-9494 | 80 | 60 |  | 20
0
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 (Done on time) | 2025-12-24 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | No Epic | 20 | 20 |  | 5.7143
Scenario Analysis (Chapter 7) | Venkatesh? (TBC) |  | Fri, 13 Feb 2026 | Fri, 20 Feb 2026 | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | VER10-8958 | 140 | 100 |  | 34.2857
Star Rates | Minas? (TBC) |  | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-13 | 2026-02-13 | No Epic | 90 | 60 |  | 21.4286
TPE | Venkatesh |  | 2026-01-23 | 2026-01-28 | 2026-02-06 | N/A | 2026-02-13 | 2026-02-13 | VER10-9184 | 350 | 160 |  | 72.8571
Dashboards (Power BI) | Minas |  | 2025-12-24 | 2025-12-31 | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | No Epic | 40 | 40 |  | 11.4286
Contractor Fee Library | Minas |  | 2026-01-09 | 2026-01-14 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | VER10-9271 | 90 | 80 |  | 24.2857
System Access | Minas |  | 2026-01-16 | N/A | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | No Epic | 40 | 40 |  | 11.4286
Audit Log | Minas |  | 2026-01-30 | 2026-02-06 | N/A | 2026-02-13 | ? |  | VER10-8955 | 10 | 11 |  | 3
WBS Tags and Custom Fields | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8916, VER10-8268 | Need Estimate | Need Estimate |  | 0
Reporting Foundation Admin | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8476 | 19 | 19 |  | 5.4286
Inflation | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8903, VER10-8570 | 41 | 41 |  | 11.7143
0
AR and O&M fixed reports |  |  | Done | Done | Done | Done | Done | Done | VER10-7878, VER10-7879 | 47 | 47 |  | 13.4286
CCESS |  |  | Done | Done | Done | Done | Done | Done | VER10-6966 | 5 | 5 |  | 1.4286
[10 empty] | 2179 | 1652 |  | 547.2857
Formulas:
SA (Technical Solution Design) = [VIGO: UI/UX Design]+7
SA (Technical Solution Design) = [Internal: UI/UX Design]+7
All Design Activities Due Date = [SA (Technical Solution Design)]

## Teams Allocation
| # points / week | 2025-12-22 | 2025-12-29 | 2025-01-05 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23
Team 1 Venkatesh & Sunjeet (3 devs) | 25 | [12 empty] | Regression/UAT | UAT
Team 2 Minas & Manish (3 devs) | 25
Team 3 Minas & Vivek (2 devs) | 20
Team 4 Venkatesh & Amit (4 devs) | 30
Team 5 Minas & Laurence (2 devs) | 25
TOTAL | 125
To deliver 1500 points (weeks) | 12
To deliver 1500 points in 9 weeks (SP per week) | 166.6667
Team | Epic | Reduced Estimate | # weeks | Dependent On | Extra Weeks
Team 1 Venkatesh & Sunjeet | Carbon (incl EPD, Auto Allocate) | 350 | 14 |  | 2
Team 2 Minas & Manish | Inflation | 41 | 1.64 |  | 0.04
| LTA | 120 | 4.8 | Carbon
| Star Rates | 60 | 2.4
| Contractor Fee Library | 80 | 3.2 | IFT?
Team 3 Minas & Vivek | Reporting Foundation Admin | 19 | 0.95 |  | -1.7
| Portfolio/Programme Risk | 60 | 3
| AR and O&M fixed reports | 47 | 2.35 | Carbon & Reporting Foundation Admin
| CCESS | 5 | 0.25 | Carbon & Reporting Foundation Admin
| Carbon Report | ?
| Workflow | 35 | 1.75
| Tasks | 40 | 2
Team 4 Venkatesh & Amit | Supply Chain - Interim Forecasting Tool | 177 | 5.9 | Carbon | -0.76667
| TPE | 160 | 5.3333
Team 5 Minas & Laurence | Audit Log | 11 | 0.44 |  | -1.96
| System Access | 40 | 1.6
| Calculators/Cost Models | 20 | 0.8
| Comparator | 100 | 4
| Scenario Analysis | 80 | 3.2 | Comparator
Work Streams |  | Reduced Estimate | Team
Dashboards (Power BI) |  | 40 | Jonny?
WBS Tags and Custom Fields |  | Need Estimate | ?
Note on C1: Minas Kamel: Assumption: Teams do 25 points a day
Note on C12: Minas Kamel: Funsho's: - Auto Allocate - Carbon Reporting

## MVP Meetings
Topic | Owner | Meeting (UK timezone) | Meeting (AU timezone) | Notes
EPD/Cost to Carbon Factor | Venkatesh | Tue 23rd Dec 10PM-11PM | Wed 24th Dec 9AM-10AM | Meeting done
LTA | Minas | Wed 24th Dec 8AM-9:30AM | Wed24th Dec 7PM-8:30PM | Meeting done
TPE & Auto Allocate (Cost & Carbon) | Venkatesh | Sun 28th Dec 10PM-11:30PM | Mon 29th Dec 9AM-10:30AM | Meeting done
Scenario Analysis (Chapter 7) | Minas | Mon 29th Dec 7AM-8:30AM | Mon 29th Dec 6PM-7:30PM
Carbon Reports | Minas
Supply Chain - Interim Forecasting Tool (incl EPD) | Venkatesh | N/A | N/A | Venkatesh needs meeting with NH
Dashboards (Power BI) | Minas
Comparator | Minas
Workflow | Minas
Tasks | Minas
Calculators/Cost Models (Chapter 10) | Minas
Star Rates | Minas
Contractor Fee Library | Minas
|  | UK | AU | Status | Topic
Mark's avail. |  | Wed 24th Dec UK morning | Wed 24th AU evening | Taken | LTA
|  | Sat 27th Dec 7AM-9AM | Sat 27th Dec 6PM-8PM | X
|  | Sun 28th Dec 7AM-9AM | Sun 28th Dec 6PM-8PM | X
|  | Sun 28th Dec 10PM-11:30PM | Mon 29th Dec 9AM-10:30AM | Taken | TPE & Auto Allocate (Cost & Carbon)
|  | Mon 29th Dec 7AM-9AM | Mon 29th Dec 6PM-8PM | Taken | Scenario Analysis (Chapter 7)
|  | Mon 29th Dec 10PM-11:30PM | Tue 30th Dec 9AM-10:30AM | After MVP deadline (Mon 29th)
|  | Fri 2nd Jan UK morning | Fri 2nd Jan AU evening | After MVP deadline (Mon 29th)