## Work Plan - Review SP (WIP)
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Epics | Story Point Estimate for Dev |  | Assumed Estimate | Team Days (current 25SP/d)
Estimate Build – Carbon | Venkatesh & Funsho |  | 2025-12-24 | 2025-12-30 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 | VER10-8954, VER10-9428, VER10-9464, VER10-9527, VER10-9523 | 575 | 414 |  | 141.2857
Interim Forecasting Tool | Venkatesh |  | 2026-01-09 | 2026-01-13 | 2026-01-21 | N/A | 2026-01-28 | 2026-01-28 | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 |  | 53.8571
Long-Term Appraisal | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8565 | 260 | 200 |  | 65.7143
Comparator | Funsho | Y | 19/12/2025 (Done on time) | 2025-12-24 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8953 | 120 | 100 |  | 31.4286
Workflow | Funsho | Y | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9028 | 35 | 35 |  | 10
Tasks | Funsho |  | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9027 | 40 | 0 |  | 5.7143
Portfolio/Programme Risk | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-22 | N/A | 2026-01-29 | 2026-01-29 | VER10-9494 | 80 | 60 |  | 20
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 (Done on time) | 2025-12-24 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | No Epic | 20 | 20 |  | 5.7143
Scenario Analysis (Chapter 7) | Venkatesh? (TBC) |  | Fri, 13 Feb 2026 | Fri, 20 Feb 2026 | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | VER10-8958 | 140 | 100 |  | 34.2857
Star Rates | Minas? (TBC) |  | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-13 | 2026-02-13 | No Epic | 90 | 60 |  | 21.4286
TPE | Venkatesh |  | 2026-01-23 | 2026-01-28 | 2026-02-06 | N/A | 2026-02-13 | 2026-02-13 | VER10-9184 | 350 | 215 |  | 80.7143
Dashboards (Power BI) | Minas |  | 2025-12-24 | 2025-12-31 | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | No Epic | 40 | 40 |  | 11.4286
Contractor Fee Library | Minas |  | 2026-01-09 | 2026-01-14 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | VER10-9271 | 90 | 80 |  | 24.2857
System Access | Minas |  | 2026-01-16 | N/A | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | No Epic | 40 | 40 |  | 11.4286
Audit Log | Minas |  | 2026-01-30 | 2026-02-06 | N/A | 2026-02-13 | ? |  | VER10-8955 | 10 | 11 |  | 3
WBS Tags and Custom Fields | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8916, VER10-8268 | Need Estimate | Need Estimate |  | 0
Reporting Foundation Admin | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8476 | 19 | 19 |  | 5.4286
Inflation | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8903, VER10-8570 | 41 | 41 |  | 11.7143
AR and O&M fixed reports |  |  | Done | Done | Done | Done | Done | Done | VER10-7878, VER10-7879 | 47 | 47 |  | 13.4286
CCESS |  |  | Done | Done | Done | Done | Done | Done | VER10-6966 | 5 | 5 |  | 1.4286
[10 empty] | 2179 | 1687 |  | 552.2857
Formulas:
SA (Technical Solution Design) = [VIGO: UI/UX Design]+7
SA (Technical Solution Design) = [Internal: UI/UX Design]+7
All Design Activities Due Date = [SA (Technical Solution Design)]

## Capacity
|  | per week | whole team
Required per team per day | 7 | 35 | 175
Ideal per team per day | 8 | 40 | 200
per dev per day |  | 1.4286

## Teams Allocation
| # points / week | 2025-12-22 | 2025-12-29 | 2025-01-05 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23
Team 1 Venkatesh & Sunjeet (3 devs) | 25 | [12 empty] | Regression/UAT | UAT
Team 2 Minas & Manish (3 devs) | 25
Team 3 Minas & Vivek (2 devs) | 20
Team 4 Venkatesh & Amit (4 devs) | 30
Team 5 Minas & Laurence (2 devs) | 25
TOTAL | 125
To deliver 1500 points (weeks) | 12
To deliver 1500 points in 9 weeks (SP per week) | 166.6667
Team | Epic | Reduced Estimate | # weeks | Dependent On | Extra Weeks
Team 1 Venkatesh & Sunjeet | Carbon (incl EPD, Auto Allocate) | 455 | 18.2 |  | 6.2
| Carbon Resource Library | 55 | 2.2
| Carbon Item Library | 85 | 3.4 | Carbon Resource
| WBS Carbon & Calc | 75 | 3 | Carbon Libraries
| Baseline Assumption | 40 | 1.6
| EPD | 75 | 3
| Cost to Carbon Library | 85 | 3.4 | Carbon WBS
| Auto-Allocate | 40 | 1.6 | Carbon Libraries
| Carbon Reports | - | -
Team 2 Minas & Manish | Inflation | 41 | 1.64 |  | 2.44
| LTA | 180 | 7.2 | Carbon WBS
| Star Rates | 60 | 2.4
| Contractor Fee Library | 80 | 3.2 | IFT?
Team 3 Minas & Vivek | Reporting Foundation Admin | 19 | 0.95 |  | -1.7
| Portfolio/Programme Risk | 60 | 3
| AR and O&M fixed reports | 47 | 2.35 | Carbon & Reporting Foundation Admin
| CCESS | 5 | 0.25 | Carbon & Reporting Foundation Admin
| Carbon Reports | 40 | 2 | Carbon
| Workflow | 35 | 1.75
Team 4 Venkatesh & Amit | Supply Chain - Interim Forecasting Tool | 200 | 6.6667 | Carbon WBS | 1.8333
| TPE | 215 | 7.1667
Team 5 Minas & Laurence | Audit Log | 11 | 0.44 |  | -0.36
| System Access | 40 | 1.6
| Calculators/Cost Models | 20 | 0.8
| Comparator | 120 | 4.8 | Carbon WBS
| Scenario Analysis | 100 | 4 | Comparator
Work Streams |  | Reduced Estimate | Team
Dashboards (Power BI) |  | 40 | Jonny?
WBS Tags and Custom Fields |  | Need Estimate | ?
Note on C1: Minas Kamel: Assumption: Teams do 25 points a day
Note on C12: Minas Kamel: Funsho's: - Auto Allocate - Carbon Reporting

## MVP Meetings
Topic | Owner | Meeting (UK timezone) | Meeting (AU timezone) | Notes
EPD/Cost to Carbon Factor | Venkatesh | Tue 23rd Dec 10PM-11PM | Wed 24th Dec 9AM-10AM | Meeting done
LTA | Minas | Wed 24th Dec 8AM-9:30AM | Wed24th Dec 7PM-8:30PM | Meeting done
TPE & Auto Allocate (Cost & Carbon) | Venkatesh | Sun 28th Dec 10PM-11:30PM | Mon 29th Dec 9AM-10:30AM | Meeting done
Scenario Analysis (Chapter 7) | Minas | Mon 29th Dec 7AM-8:30AM | Mon 29th Dec 6PM-7:30PM
Carbon Reports | Minas
Supply Chain - Interim Forecasting Tool (incl EPD) | Venkatesh | N/A | N/A | Venkatesh needs meeting with NH
Dashboards (Power BI) | Minas
Comparator | Minas
Workflow | Minas
Tasks | Minas
Calculators/Cost Models (Chapter 10) | Minas
Star Rates | Minas
Contractor Fee Library | Minas
|  | UK | AU | Status | Topic
Mark's avail. |  | Wed 24th Dec UK morning | Wed 24th AU evening | Taken | LTA
|  | Sat 27th Dec 7AM-9AM | Sat 27th Dec 6PM-8PM | X
|  | Sun 28th Dec 7AM-9AM | Sun 28th Dec 6PM-8PM | X
|  | Sun 28th Dec 10PM-11:30PM | Mon 29th Dec 9AM-10:30AM | Taken | TPE & Auto Allocate (Cost & Carbon)
|  | Mon 29th Dec 7AM-9AM | Mon 29th Dec 6PM-8PM | Taken | Scenario Analysis (Chapter 7)
|  | Mon 29th Dec 10PM-11:30PM | Tue 30th Dec 9AM-10:30AM | After MVP deadline (Mon 29th)
|  | Fri 2nd Jan UK morning | Fri 2nd Jan AU evening | After MVP deadline (Mon 29th)

## Action Log
ID | Action | Owner | Raised Date | Due Date / RAG | Status
A06 | Finalise onboarding plan for 4 additional engineers chase profiles and shortlist | Jerome | 2026-01-05 | 2026-01-09 | In progress
A26 | Continue monitoring NH PRD sign-off behaviour and flag governance risk early | Richard | 2026-01-07 | Ongoing | Open
A32 | Risk around TPE and the amount if work to be done in the last Sprint | Richard/Jerome | 2026-02-15 | 2026-02-15 | In progress
A33 | Capacity / Velocity Concerns | Richard/Jerome | 2026-02-15 | 2026-02-15 | In progress

## Current Defects
Condition |  |  | Status
P1 > 0 |  |  | 🔴 Escalation
P1 = 0 AND Open defects ↑ for 2+ days |  |  | 🟠 Watch
Open defects ↓ OR steady & closures happening |  |  | 🟢 Stable
Release 1D | [5 empty] | Release 2A
Date | Raised by NH | No P1's | Total Open Defects | Total Closed Today | Daily Status | Date | No P1's | Total No Defects | Total Closed Today | Daily Status
14/01/2026 | 0 | 0 | 27 | 2 | 🟢 Stable | 14/01/2026
15/01/2026 | 0 | 0 | 27 | 0 | 🟢 Stable | 15/01/2026 | 0 | 0 | 0 | 🟢 Stable
16/01/2026 | 0 | 0 | 24 | 3 | 🟢 Stable | 16/01/2026 | 0 | 0 | 0 | 🟢 Stable
17/01/2026 | [5 empty] | 17/01/2026
18/01/2026 | [5 empty] | 18/01/2026
19/01/2026 | 0 | 0 | 23 | 1 | 🟢 Stable | 19/01/2026 | 0 | 0 | 0 | 🟢 Stable
20/01/2026 | 0 | 0 | 18 | 5 | 🟢 Stable | 20/01/2026 | 0 | 0 | 0 | 🟢 Stable
21/01/2026 | 0 | 0 | 16 | 2 | 🟢 Stable | 21/01/2026 | 0 | 0 | 0 | 🟢 Stable
22/01/2026 | 0 | 0 | 15 | 1 | 🟢 Stable | 22/01/2026 | 0 | 0 | 0 | 🟢 Stable
23/01/2026 | 0 | 0 | 13 | 0 | 🟢 Stable | 23/01/2026 | 0 | 0 | 0 | 🟢 Stable
24/01/2026 | [5 empty] | 24/01/2026
25/01/2026 | [5 empty] | 25/01/2026
26/01/2026 | 0 | 0 | 13 | 0 | 🟢 Stable | 26/01/2026 | 0 | 0 | 0 | 🟢 Stable
27/01/2026 | TBC | 0 | 11 | 2 | 🟢 Stable | 27/01/2026 | 0 | 0 | 0 | 🟢 Stable
28/01/2026 | [5 empty] | 28/01/2026
29/01/2026 | [5 empty] | 29/01/2026
30/01/2026 | [5 empty] | 30/01/2026
31/01/2026 | [5 empty] | 31/01/2026
01/02/2026 | [5 empty] | 01/02/2026
Master R1D Defect View - BMJIRA

## Stage Gate Tracker
Gate | Owner | Rationale | Pass Criteria (Evidence Required) | SPRINT 35 | Carbon Resource Library | Carbon Item Library | System Access | Audit Log | WBS Tags and Custom Fields | SPRINT 36 | Long-Term Appraisal | Cost to Carbon Library | Portfolio/Programme Risk | WBS Carbon & Calc | Comparator | SPRINT 37 | Star Rates | Inflation | AR and O&M fixed reports | EPD | Workflow | Auto-Allocate | Interim Forecasting Tool (incl EPD) | Carbon Reports | SPRINT 38 | Scenario Analysis (Chapter 7) | TPE | Dashboards (Power BI) | Reporting Foundation Admin
SCOPE REFINEMENT
1. Individual PRDs Drafted | Minas | Ensures scope and requirements are explicit before design and build begin, avoiding downstream rework and ambiguity. |  |  | Sprint 35 | Sprint 35 | Sprint 35 | Sprint 35 | Sprint 35 |  | Sprint 36+37 | Sprint 36 | Sprint 36 | Sprint 36+37 | Sprint 36+37 |  | Sprint 38 | Sprint 38 | Sprint 38 | Sprint 38 | Sprint 38 | Sprint 38 | Sprint 38+39 | Sprint 38 |  | Sprint 39 | Sprint 39 | Sprint 39 | Sprint 39
|  |  | • PRDs drafted for each of the MVP epics |  | 2025-12-24 | 2025-12-24 | Done | 2026-01-09 | Done |  | 2025-12-12 | 2025-12-24 | 2025-12-12 | 2025-12-24 | 2025-12-12 |  | 2026-02-06 | Done | Done | 2025-12-24 | 2025-12-17 | 2025-12-24 | 2026-01-09 | No PRD Req |  | 2026-01-23 | 2026-01-30 | 2026-01-09 | Done
|  |  | • Functional requirements prioritised (Must / Should / Deferred) |  | 2025-12-24 | 2025-12-24 | Done | 2026-01-09 | Done |  | 2025-12-12 | 2025-12-24 | 2025-12-12 | 2025-12-24 | 2025-12-12 |  | 2026-02-06 | Done | Done | 2025-12-24 | 2025-12-17 | 2025-12-24 | 2026-01-09 | No PRD Req |  | 2026-01-23 | 2026-01-30 | 2026-01-09 | Done
|  |  | • In-scope vs out-of-scope clearly defined |  | 2025-12-24 | 2025-12-24 | Done | 2026-01-09 | Done |  | 2025-12-12 | 2025-12-24 | 2025-12-12 | 2025-12-24 | 2025-12-12 |  | 2026-02-06 | Done | Done | 2025-12-24 | 2025-12-17 | 2025-12-24 | 2026-01-09 | No PRD Req |  | 2026-01-23 | 2026-01-30 | 2026-01-09 | Done
|  |  | • Dependencies and assumptions explicitly documented |  | 2025-12-24 | 2025-12-24 | Done | 2026-01-09 | Done |  | 2025-12-12 | 2025-12-24 | 2025-12-12 | 2025-12-24 | 2025-12-12 |  | 2026-02-06 | Done | Done | 2025-12-24 | 2025-12-17 | 2025-12-24 | 2026-01-09 | No PRD Req |  | 2026-01-23 | 2026-01-30 | 2026-01-09 | Done
2. PRDs Reviewed & Signed Off (NH) | Richard | Confirms shared understanding and agreement with NH to prevent late scope disputes or rework. | • NH review completed |  | 2026-01-08 | 2026-01-08 | Done | 2026-01-16 | Done |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-08 | 2026-01-21 |  | 2023-02-11 | Done | Done | 2026-01-08 | 2026-01-08 | 2026-01-16 | 2026-01-16 | N/A |  | 2026-01-30 | 2026-02-06 | 2026-01-14 | Done
|  |  | • Explicit NH sign-off received |  | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
|  |  | • No open scope alignment questions |  | 2026-01-09 | 2026-01-09 | Done | 2026-01-16 | Done |  | 2026-01-23 | 2026-01-18 | 2026-01-18 | 2026-01-09 | 2026-01-23 |  | 2023-02-11 | Done | Done | 2026-01-09 | 2026-01-09 | 2026-01-18 | 2026-01-16 | N/A |  | 2026-01-30 | 2026-02-06 | 2026-01-16 | Done
|  |  | • Any gaps documented, escalated and resolved |  | 2026-01-09 | 2026-01-09 | Done | 2026-01-16 | Done |  | 2026-01-23 | 2026-01-18 | 2026-01-18 | 2026-01-09 | 2026-01-23 |  | 2023-02-11 | Done | Done | 2026-01-09 | 2026-01-09 | 2026-01-18 | 2026-01-16 | N/A |  | 2026-01-30 | 2026-02-06 | 2026-01-16 | Done
DESIGN STAGES
3. UX/UI Designs Completed | Richard (coordination) | Prevents design churn during development and ensures build teams are working from stable designs. | • UX/UI designs completed for all in-scope MVP flows |  | 2026-01-09 | 2026-01-09 | Done | Done | Done |  | 2026-01-30 | 2026-01-23 | 2026-01-23 | 2026-01-16 | 2026-01-23 |  | 2023-02-13 | Done | Done | 2026-01-23 | 2026-01-20 | 2026-01-23 | 2026-01-23 | 2026-02-06 |  | 2026-02-06 | 2026-02-13 | 2026-02-12 | Done
|  |  | • Designs reviewed and accepted internally |  | 2026-01-09 | 2026-01-09 | Done | Done | Done |  | 2026-01-30 | 2026-01-23 | 2026-01-23 | 2026-01-16 | 2026-01-23 |  | 2023-02-13 | Done | Done | 2026-01-23 | 2026-01-20 | 2026-01-23 | 2026-01-23 | 2026-02-06 |  | 2026-02-06 | 2026-02-13 | 2026-02-12 | Done
|  |  | • Ownership agreed (Vigo vs in-house) |  | 2026-01-09 | 2026-01-09 | Done | Done | Done |  | 2026-01-30 | 2026-01-23 | 2026-01-23 | 2026-01-16 | 2026-01-23 |  | 2023-02-13 | Done | Done | 2026-01-23 | 2026-01-20 | 2026-01-23 | 2026-01-23 | 2026-02-06 |  | 2026-02-06 | 2026-02-13 | 2026-02-12 | Done
|  |  | • No critical design work outstanding for sprint execution |  | 2026-01-09 | 2026-01-09 | Done | Done | Done |  | 2026-01-30 | 2026-01-23 | 2026-01-23 | 2026-01-16 | 2026-01-23 |  | 2023-02-13 | Done | Done | 2026-01-23 | 2026-01-20 | 2026-01-23 | 2026-01-23 | 2026-02-06 |  | 2026-02-06 | 2026-02-13 | 2026-02-12 | Done
4. Solution Architectures (SAs) Drafted | Richard (coordination) | Grounds delivery commitments in technical reality and surfaces assumptions, risks, and trade-offs early. | • SAs drafted for each epic |  | 2026-01-14 | 2026-01-14 | Done | Done | Done |  | 2026-02-04 | 2026-01-29 | 2026-01-29 | 2026-01-23 | 2026-01-29 |  | 2023-02-20 | Done | Done | 2025-01-29 | 2026-01-26 | 2025-01-29 | 2025-01-29 | 2026-02-12 |  | 2026-02-13 | 2026-02-20 | 2026-02-12 | Done
|  |  | • Architecture simplified to MVP |  | 2026-01-14 | 2026-01-14 | Done | Done | Done |  | 2026-02-04 | 2026-01-29 | 2026-01-29 | 2026-01-23 | 2026-01-29 |  | 2023-02-20 | Done | Done | 2025-01-29 | 2026-01-26 | 2025-01-29 | 2025-01-29 | 2026-02-12 |  | 2026-02-13 | 2026-02-20 | 2026-02-12 | Done
|  |  | • Technical assumptions and risks explicit |  | 2026-01-14 | 2026-01-14 | Done | Done | Done |  | 2026-02-04 | 2026-01-29 | 2026-01-29 | 2026-01-23 | 2026-01-29 |  | 2023-02-20 | Done | Done | 2025-01-29 | 2026-01-26 | 2025-01-29 | 2025-01-29 | 2026-02-12 |  | 2026-02-13 | 2026-02-20 | 2026-02-12 | Done
|  |  | • Key trade-offs documented |  | 2026-01-14 | 2026-01-14 | Done | Done | Done |  | 2026-02-04 | 2026-01-29 | 2026-01-29 | 2026-01-23 | 2026-01-29 |  | 2023-02-20 | Done | Done | 2025-01-29 | 2026-01-26 | 2025-01-29 | 2025-01-29 | 2026-02-12 |  | 2026-02-13 | 2026-02-20 | 2026-02-12 | Done
5. SAs Reviewed & Approved | Jerome | Locks technical feasibility before commitments are made and avoids late architectural rework. | • SAs reviewed and approved |  | 2026-01-16 | 2026-01-16 | Done | Done | Done |  | 2026-02-06 | 2026-01-29 | 2026-01-29 | 2026-01-23 | 2026-01-29 |  | 2023-02-23 | Done | Done | 2025-01-29 | 2026-01-26 | 2025-01-29 | 2025-01-29 | 2026-02-12 |  | 2026-02-13 | 2026-02-20 | 2026-02-12 | Done
|  |  | • Risks accepted or mitigated |  | 2026-01-16 | 2026-01-16 | Done | Done | Done |  | 2026-02-06 | 2026-01-29 | 2026-01-29 | 2026-01-23 | 2026-01-29 |  | 2023-02-23 | Done | Done | 2025-01-29 | 2026-01-26 | 2025-01-29 | 2025-01-29 | 2026-02-12 |  | 2026-02-13 | 2026-02-20 | 2026-02-12 | Done
|  |  | • No unresolved feasibility questions |  | 2026-01-16 | 2026-01-16 | Done | Done | Done |  | 2026-02-06 | 2026-01-29 | 2026-01-29 | 2026-01-23 | 2026-01-29 |  | 2023-02-23 | Done | Done | 2025-01-29 | 2026-01-26 | 2025-01-29 | 2025-01-29 | 2026-02-12 |  | 2026-02-13 | 2026-02-20 | 2026-02-12 | Done
|  |  | • Delivery implications understood by Delivery Manager |  | 2026-01-16 | 2026-01-16 | Done | Done | Done |  | 2026-02-06 | 2026-01-29 | 2026-01-29 | 2026-01-23 | 2026-01-29 |  | 2023-02-23 | Done | Done | 2025-01-29 | 2026-01-26 | 2025-01-29 | 2025-01-29 | 2026-02-12 |  | 2026-02-13 | 2026-02-20 | 2026-02-12 | Done
6. Performance-Aware Design Approved | Yoong | Ensures design and architectural decisions do not inherently introduce performance, scalability, or data-related risk. | • NFR defined (SLOs, throughput, user capacity) |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16
|  |  | • Scalability expectations, complexity and data volume projections documented |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16
|  |  | • Database schema optimised with indexing strategy |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16
|  |  | • APIs follows performance best practices |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16
SPRINT SCHEDULING
7. Sprint Planning by Epic Completed | Richard | Ensures execution commitments are realistic, capacity-aligned, and dependency-aware before development starts. | • Sprint plan complete by epic |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-12 |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19
|  |  | • Scope aligned to PRDs, UX/UI, and SAs |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-12 |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19
|  |  | • Dependencies explicit |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-12 |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19
|  |  | • Capacity and story points validated |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-12 |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19
EXECUTION / DELIVERY
8. Development Complete & Code Integrated | Richard | Confirms committed sprint scope is fully built and integrated into the shared codebase, ready for formal QA/system testing. | • All committed stories meet Definition of Done |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12
|  |  | • Code merged to agreed branch with peer reviews completed |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12
|  |  | • Sprint review completed and recorded |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12
|  |  | • Integration complete across in-scope components |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12
|  |  | • No gating integration issues preventing QA execution |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12
9. System/QA Testing Completed | Owner: Hema Oversight: Caroline | Purpose: Validates functional correctness, system stability, and regression safety prior to Internal and NH UAT. Exit Evidence: QA summary report, defect status, QA sign-off | • Unit testing completed for all in-scope BE/FE components |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12
|  |  | • Full regression testing executed: • All epics deployed to Regression • End-to-end regression pass completed (≈ 5 days) • Deployment approach confirmed with Dev teams (Yoong) |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19
|  |  | • Defect position agreed: • Critical / High defects resolved, or • Explicitly accepted with documented risk and approval |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19
|  |  | • QA Test Summary Report completed and shared (Hema) |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19
|  |  | • Formal QA sign-off provided (Hema, with Caroline review) |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20
10. Platform Performance & System Readiness Approved Dependencies / risks: Observability capability requires build-out | Yoong | Purpose: Confirms the system can safely operate at expected scale without unacceptable performance, stability, or reliability risk. Exit Evidence: Performance results, monitoring confirmation, readiness sign-off | • Data Load & Scale – Performance and load tests executed – Results conform to agreed thresholds (capacity headroom, error rate) – Estimated duration: 2–3 days |  | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23
|  |  | • Regression Protection – No performance degradation beyond agreed threshold (≤5%) |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24
|  |  | • Observability & Recovery – Monitoring and alerting operational – Logging and diagnostics available to support UAT defect triage – Recovery / rollback approach defined |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24
11. DevOps Deployment to UAT | Jerome | Ensures the solution is correctly deployed, configured, and stable in the UAT environment. QA sign-off (Stage 9) Platform readiness approval (Stage 10) | • Successful deployment to UAT completed – Deployment executed from approved code baseline – Known risk: data-related challenges (tracked and communicated) |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 |  | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25
|  |  | • Environment configuration validated – Feature flags, config values, integrations aligned to release scope |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 |  | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26
|  |  | • Monitoring, logging, and rollback in place |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 |  | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26
|  |  | • Release notes shared with Internal UAT |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 |  | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26
12. Internal UAT | Caroline | Validates end-to-end functionality, stability, and UAT readiness through internal scenario execution, defect triage, and stakeholder artefact preparation prior to NH business testing. Exit evidence: Internal UAT status, defect summary, readiness confirmation | • Internal UAT execution completed for all in-scope scenarios |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02
|  |  | • Defects triaged and dispositioned (fix / defer / accept) |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02
|  |  | • External UAT environment confirmed ready |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02
|  |  | • Demo recording completed for NH |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-03
|  |  | • Training documentation completed and internally reviewed for NH |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06
|  |  | • Release notes, training docs and demo shared with NH UAT stakeholders |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06
13. NH UAT Completed & Accepted | Caroline | Confirms solution meets business needs and is approved for production readiness. Outcome: Release approved for onward promotion (subject to programme governance) | • UAT scenarios executed for all in-scope flows |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20
|  |  | • Business acceptance criteria met |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20
|  |  | • No unresolved critical/high UAT defects |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20
|  |  | • Formal UAT sign-off received |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21
Formulas:
Cost to Carbon Library = [Cost to Carbon Library, row above]
Auto-Allocate = [Auto-Allocate, row above]

## Work Plan V3
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Dev Start | Dev Finish | SG1 | SG2 | SG3 | SG4 | SG5 | SG6 | SG7 | SG8 | SG9 | SG10 | SG11 | SG12 | Epics | Original Estimate | Updated Estimate | Priority | Allocated Team | Team Work Days (7 SP pd) | Team Work Days (8 SP pd) | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | Total
Carbon Resource Library | Venkatesh |  | 2025-12-24 | 2026-01-07 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-16 | Sprint 35 | Sprint 35 | √ | √ | √ | √ | √ | √ | √ | [5 empty] | https://benchmarkestimating.atlassian.net/browse/VER10-9428 | 575 | 55 | 1 | Team 1 | 7.8571 | 6.875 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | [65 empty] | 9
Carbon Item Library | Venkatesh |  | 2025-12-24 | 2026-01-07 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-16 | Sprint 35 | Sprint 35 | √ | √ | √ | √ | √ | √ | √ | [5 empty] | https://benchmarkestimating.atlassian.net/browse/VER10-9373 |  | 85 | 2 | Team 4 | 12.1429 | 10.625 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 11
Import / Export | Venkatesh |  | 2025-12-24 | 2026-01-07 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-16 | Sprint 35 | Sprint 35 | √ | √ | √ | √ | √ | √ | √ | [26 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F
WBS Carbon & Calc | Venkatesh / Amit S. |  | 2025-12-24 | 2026-01-09 | 2026-01-30 | N/A | 2026-01-30 | 2026-01-30 | Sprint 36 | Sprint 37 | √ | √ | √ | [11 empty] | 75 | 4 | Team 4 | 10.7143 | 9.375 | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 11
EPD | Venkatesh / Sunjeet |  | 2025-12-24 | 2026-01-23 | 2026-01-30 | N/A | 2026-02-05 | 2026-02-05 | Sprint 37 | Sprint 37 | √ | [13 empty] | 75 | 5 | Team 1 | 10.7143 | 9.375 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | F | [29 empty] | 14
Cost to Carbon Library | Venkatesh / Sunjeet |  | 2025-12-24 | 2026-01-23 | 2026-02-06 | N/A | 2026-02-13 | 2026-02-13 | Sprint 37 | Sprint 38 | √ | √ | [12 empty] | 85 | 7 | Team 1 | 12.1429 | 10.625 | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 11
Auto-Allocate | Venkatesh / Amit S |  | 2025-12-24 | 2026-01-23 | 2026-02-10 | N/A | 2026-02-13 | 2026-02-13 | Sprint 37 | Sprint 37 | √ | [13 empty] | 40 | 6 | Team 4 | 5.7143 | 5 | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 11
Interim Forecasting Tool (incl EPD) | Venkatesh |  | Fri 12 Dec 2025 | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-06 | Sprint 35 | Sprint 39 | √ | √ | √ | √ | √ | √ | √ | [5 empty] | VER10-8678, VER10-8680, VER10-8682, VER10-8858, VER10-8679, VER10-8921, VER10-9049, VER10-9128 | 177 | 200 | 1 | Team 4 | 28.5714 | 25 |  |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 40
Long-Term Appraisal | Minas / Manish |  | Fri 12 Dec 2025 | 2026-01-23 | 2026-01-30 | N/A | 2026-01-30 | 2026-01-30 | Sprint 36 | Sprint 37 | √ | √ | [10 empty] | VER10-9697, VER10-9698, VER10-9699, VER10-9700, VER10-9701, VER10-9702 | 260 | 180 | 4 | Team 2 | 25.7143 | 22.5 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | F | [37 empty] | 19
Comparator | Minas / Laurence | Y | Fri 12 Dec 2025 | 2026-01-19 | 2026-01-26 | N/A | 2026-01-30 | 2026-01-30 | Sprint 36 | Sprint 37 | √ | √ | [10 empty] | VER10-8953 | 120 | 120 | 4 | Team 5 | 17.1429 | 15 | [31 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 10
Carbon Reports | Minas / Vivek |  | 2026-01-09 | 2026-01-16 | N/A | N/A | 2026-02-13 | 2026-02-13 | Sprint 37 | Sprint 38 | [14 empty] | 40 |  | Team 3 | 5.7143 | 5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [35 empty] | 10
Workflow | Minas / Vivek | Y | Fri 12 Dec 2025 | 2026-01-30 | 2026-02-13 | N/A | 2026-02-20 | 2026-02-20 | Sprint 38 | Sprint 38 | √ | [11 empty] | VER10-9028 | 35 | 35 | 5 | Team 3 | 5 | 4.375 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 11
Portfolio/Programme Risk | Minas / Vivek |  | Fri 12 Dec 2025 | Mon 22 Dec 2025 | 2026-01-30 | N/A | 2026-01-30 | 2026-01-30 | Sprint 36 | Sprint 36 | √ | √ | √ | [9 empty] | VER10-9494 | 80 | 60 | 5 | Team 3 | 8.5714 | 7.5 | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 11
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 | Fri 9 Jan 2025 | N/A | N/A | 2026-01-23 | 2026-01-23 | Sprint 35 | Sprint 35 | √ | √ | √ | [9 empty] | No Epic | 20 | 20 | 6 | Team 5 | 2.8571 | 2.5 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 11
Scenario Analysis (Chapter 7) | Minas? (TBC) |  | 2026-01-23 | 2026-02-13 | 2026-02-20 | N/A | 2026-02-27 | 2026-02-27 | Sprint 38 | Sprint 39 | √ | [11 empty] | VER10-8958 | 140 | 100 | 5 | Team 3 | 14.2857 | 12.5 | [56 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [21 empty] | 10
Star Rates | Minas? (TBC) |  | 2026-02-06 | 2026-02-11 | N/A | 2026-02-13 | 2026-02-13 | 2026-02-13 | Sprint 37 | Sprint 37 | [12 empty] | No Epic | 90 | 60 |  | Team 2 | 8.5714 | 7.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 11
TPE | Venkatesh |  | 2026-01-30 | 2026-02-06 | 2026-02-20 | N/A | 2026-02-27 | 2026-02-27 | Sprint 38 | Sprint 39 | [12 empty] | VER10-9184 | 350 | 215 | 4 | Team 5 | 30.7143 | 26.875 | [56 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [21 empty] | 10
Dashboards (Power BI) | Minas |  | 2026-01-09 | N/A | N/A | N/A | N/A | N/A | Sprint 38 | Sprint 38 | √ | [11 empty] | No Epic | 40 | 40 | 2 | Dashboard Team | 5.7143 | 5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 11
Contractor Fee Library | Minas |  | 2026-02-13 | 2026-02-18 | N/A | 2026-02-20 | 2026-02-27 | 2026-02-27 | Sprint 38 | Sprint 38 | [12 empty] | VER10-9271 | 90 | 80 | 3 | Team 2 | 11.4286 | 10 | [56 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [21 empty] | 10
System Access | Minas |  | 2026-01-09 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 | 2026-01-23 | Sprint 35 | Sprint 35 | [12 empty] | VER10-8452 | 40 | 40 | 3 | Team 5 | 5.7143 | 5 |  |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 20
Audit Log | Minas |  | Done | Done | Done | 2026-01-23 | 2026-01-29 | 2026-01-29 | Sprint 35 | Sprint 35 | √ | √ | √ | √ | √ | √ | √ | [5 empty] | VER10-8955, VER10-6972 | 10 | 11 |  | Team 5 | 1.5714 | 1.375 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 11
WBS Tags and Custom Fields | Minas / Manish |  | Done | Done | Done | Done | Done | Done | Sprint 36 | Sprint 36 | √ | √ | √ | √ | √ | √ | √ | [5 empty] | VER10-8916, VER10-8268 | 10 | 10 |  | Team 2 | 1.4286 | 1.25 | [6 empty] | X | F | [6 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 12
Custom Field Filtering | Minas |  | Done | Done | Done | Done | Done | Done | Sprint 35 | Sprint 35 | √ | √ | √ | √ | √ | √ | √ | [40 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F
Reporting Foundation Admin | Minas / Vivek |  | Done | Done | Done | Done | Done | Done | Sprint 36 | Sprint 36 | √ | √ | √ | √ | √ | √ | √ | [5 empty] | VER10-8476 | 19 | 19 |  | Team 3 | 2.7143 | 2.375 |  |  |  |  | X | X | X | F | [6 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 14
Inflation | Minas |  | Done | Done | Done | Done | Done | Done | Sprint 37 | Sprint 37 | √ | √ | √ | √ | √ | √ | [6 empty] | VER10-8903, VER10-8570 | 41 | 41 |  | Team 3 | 5.8571 | 5.125 | [10 empty] | X | X | X | X | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 15
AR and O&M fixed reports | Minas |  | Done | Done | Done | Done | Done | Done | Sprint 37 | Sprint 37 | √ | √ | √ | √ | √ | √ | [6 empty] | VER10-7878, VER10-7879 | 47 | 47 |  | Team 3 | 6.7143 | 5.875 | [7 empty] | X |  |  | X | X | X | X | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 16
CCESS | Minas |  | Done | Done | Done | Done | Done | Done | Sprint 37 | Sprint 37 | √ | √ | √ | √ | [8 empty] | VER10-6966 | 5 | 5 |  | Team 3 | 0.71429 | 0.625 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 11
[24 empty] | 2149 | 1738 | 1805 |  | 248.2857 | 217.25 | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 3 | 0 | 0 | 4 | 4 | 4 | 4 | 9 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 9 | 9 | 9 | 9 | 15 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 9 | 9 | 9 | 9 | 16 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 9 | 9 | 8 | 8 | 10 | 0 | 0 | 4 | 4 | 4 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330
Key | For this week | [25 empty] | Team 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
| Complete | [25 empty] | Team 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
| At risk (Mitigation) | [25 empty] | Team 3 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 6 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98
| Blocked/Late | [25 empty] | Team 4 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 4 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
[27 empty] | Team 5 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62
Sprint Dates | Starts |  | Ends | [23 empty] | Total |  |  | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 3 | 0 | 0 | 4 | 4 | 4 | 4 | 7 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 7 | 7 | 7 | 8 | 13 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 14 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 7 | 7 | 9 | 0 | 0 | 4 | 4 | 4 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 35 | 19/01/26 |  | 02/02/26
Sprint 36 | 02/02/26 |  | 16/02/26
Sprint 37 | 16/02/26 |  | 02/03/26
Sprint 38 | 02/03/26 |  | 16/03/26
Sprint 39 | 16/03/26 |  | 27/03/26
Formulas:
N/A = [N/A]+7
Note on C17: Minas Kamel: Richard?

## ESCALATIONS
Escalations Week Commencing 26-Jan
Escalation Date | Escalation | Raised by | Stage Gate | Escalation Owner | Due Date | RAG | Resolved Date | Commentary
Week Commencing (12th) | PRD Review - IFT | Richard | SG2 - NH Sign-Off | Richard | 16/01/2026 |  | 23/01/2026 | NH review completed / Sprint 39 to be added so replan can happen
22/01/2026 | SA - Import/Export | Richard | SG5 -SA Review | Yoong |  |  |  | No import/export in SG tracker?
22/01/2026 | SA - Cost Models/Calculators | Richard | SG5 -SA Review | Jerome |  |  |  | No Cost models/Calcs in SG tracker?
27/01/2026 | LTA UI/UX + SA at risk for 30/01/2026 | Minas | SG3 + SG4 | Richard
27/01/2026 | Comparator UI/UX at risk | Minas | SG3 | Richard
27/01/2026 | Review of Sprint Plan / Sequencing of PRD/SA etc | Minas |  | Richard
🟢 Green – On track / no dependency risk
🟡 Amber – Dependency, waiting on decision/input
🔴 Red – Missed date, blocking delivery, escalation needed

## Work Plan
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Epics | Original Estimate | Updated Estimate | Priority | Allocated Team | Team Days (current 25SP/d) | Team Days (Uplifted 30SP/d) | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | Total
Estimate Build – Carbon (incl. EPD) | Venkatesh& Minas |  | 2025-12-24 | [5 empty] | VER10-8954, VER10-9428, VER10-9464, VER10-9527, VER10-9523 | 575 | 495 |  | 2 x Teams | 70.7143 | 30.9375 | [73 empty] | 0
Carbon Resource Library | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 55 | 1 | Team 1 | 8 | 7 | [7 empty] | X |  |  | X | X | X | X | X |  |  | X | F | [54 empty] | 7
Carbon Item Library | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 85 | 2 | Team 4 | 12.4286 | 10.875 | [7 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [48 empty] | 11
WBS Carbon & Calc | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 75 | 4 | Team 4 | 11.2857 | 9.875 | [24 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [34 empty] | 10
Baseline Assumption | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 40 | 3 | Team 1 | 6.1429 | 5.375 | [19 empty] | X | X | X |  |  | X | X | F | [46 empty] | 5
EPD | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 75 | 5 | Team 1 | 11.4286 | 10 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | F | [31 empty] | 10
Cost to Carbon Library | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 85 | 7 | Team 1 | 13.1429 | 11.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [12 empty] | 12
Auto-Allocate | Venkatesh |  | 2025-12-24 | 2026-01-09 | [6 empty] | 40 | 6 | Team 4 | 6.5714 | 5.75 | [39 empty] | X | X | X | X |  |  | X | X | F | [25 empty] | 6
Carbon Reports | MInas |  | ? | 2026-01-09 | [6 empty] | 40 |  | Team 3 | 5.7143 | 5 | [52 empty] | X | X | X | X | X |  |  | F | [13 empty] | 5
Interim Forecasting Tool (incl EPD) | Venkatesh |  | 2026-01-09 | 2026-01-13 | 2026-01-21 | N/A | 2026-01-28 | 2026-01-28 | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 | 1 | Team 4 | 28.7143 | 25.125 | X |  |  | X | X | X | X | [32 empty] | X | X | X | X | X |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [9 empty] | 24
Long-Term Appraisal | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8565 | 260 | 180 | 4 | Team 2 | 26.2857 | 11.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [12 empty] | 12
Comparator | Funsho | Y | 19/12/2025 (Done on time) | 2025-12-24 | 2026-01-15 | N/A | 2026-01-22 | 2026-01-22 | VER10-8953 | 120 | 120 | 4 | Team 5 | 17.7143 | 15.5 | [38 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [12 empty] | 16
Workflow | Funsho | Y | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9028 | 35 | 35 | 5 | Team 3 | 5.7143 | 5 |  |  |  | X | X | X | X | X |  |  | F | [62 empty] | 5
Tasks | Funsho |  | Wed 17 Dec 2025 (1 day delay) | 2025-12-19 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | VER10-9027 | 40 | 0 |  | N/A | 0 | 0 | [73 empty] | 0
Portfolio/Programme Risk | Funsho |  | Fri 12 Dec 2025 (Done on time) | 2025-12-17 | 2026-01-22 | N/A | 2026-01-29 | 2026-01-29 | VER10-9494 | 80 | 60 | 5 | Team 3 | 9.2857 | 8.125 | [38 empty] | X | X | X | X | X |  |  | X | X | X | F | [24 empty] | 8
[14 empty] | 0 | 0 | [73 empty] | 0
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 (Done on time) | 2025-12-24 | N/A | 2026-01-09 | 2026-01-16 | 2026-01-16 | No Epic | 20 | 20 | 6 | Team 5 | 3.7143 | 3.25 |  |  |  | X | X | X | [67 empty] | 3
Scenario Analysis (Chapter 7) | Venkatesh? (TBC) |  | Fri, 13 Feb 2026 | Fri, 20 Feb 2026 | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | VER10-8958 | 140 | 100 | 5 | Team 5 | 15 | 13.125 | [24 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  |  | X | X | X | [31 empty] | 13
Star Rates | Minas? (TBC) |  | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-13 | 2026-02-13 | No Epic | 90 | 60 |  | Team 2 | 8.5714 | 7.5 | [10 empty] | X | X | X | X | X |  |  | X | X | X | F | [52 empty] | 8
TPE | Venkatesh |  | 2026-01-23 | 2026-01-28 | 2026-02-06 | N/A | 2026-02-13 | 2026-02-13 | VER10-9184 | 350 | 215 | 4 | Team 4 | 31.2857 | 27.375 | [73 empty] | 0
Dashboards (Power BI) | Minas |  | Fri, 16 Jan 2026 (Original 24/12/2025) | Wed, 21 Jan 2026 (Original 31/12/2025) | 2026-01-29 | N/A | 2026-02-05 | 2026-02-05 | No Epic | 40 | 40 | 2 | Dashboard Team | 6 | 5.25 | [38 empty] | X | X | X | X | X |  |  | X | F | [26 empty] | 6
Contractor Fee Library | Minas |  | 2026-01-09 | 2026-01-14 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | VER10-9271 | 90 | 80 | 3 | Team 2 | 11.8571 | 10.375 | [20 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | F | [38 empty] | 10
System Access | Minas |  | 2026-01-16 | N/A | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | No Epic | 40 | 40 | 3 | Team 5 | 6.1429 | 5.375 | [73 empty] | 0
Audit Log | Minas |  | 2026-01-30 | 2026-02-06 | N/A | 2026-02-13 | ? |  | VER10-8955 | 10 | 11 |  | Team 5 | 1.5714 | 1.375 | [73 empty] | 0
WBS Tags and Custom Fields | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8916, VER10-8268 | Need Estimate | Need Estimate |  | Team 3 | 0 | 0 | [73 empty] | 0
Reporting Foundation Admin | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8476 | 19 | 19 |  | Team 3 | 2.7143 | 2.375 | [10 empty] | X | X | F | [60 empty] | 2
Inflation | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8903, VER10-8570 | 41 | 41 |  | Team 2 | 5.8571 | 5.125 | [34 empty] | X | X |  |  | X | X | X | X | F | [30 empty] | 6
[14 empty] | 0 | 0 | [73 empty] | 0
AR and O&M fixed reports |  |  | Done | Done | Done | Done | Done | Done | VER10-7878, VER10-7879 | 47 | 47 |  | Team 3 | 6.7143 | 5.875 | [24 empty] | X | X | X | X | X |  |  | X | F | [40 empty] | 6
CCESS |  |  | Done | Done | Done | Done | Done | Done | VER10-6966 | 5 | 5 |  | Team 3 | 0.71429 | 0.625 | [32 empty] | X | F | [39 empty] | 1
[10 empty] | 2179 | 1768 | 2333 |  | 333.2857 | 249.1875 | 1 | 0 | 0 | 3 | 3 | 3 | 2 | 3 | 0 | 0 | 4 | 4 | 3 | 3 | 3 | 0 | 0 | 3 | 2 | 3 | 3 | 3 | 0 | 0 | 5 | 5 | 4 | 5 | 5 | 0 | 0 | 5 | 5 | 4 | 4 | 4 | 0 | 0 | 5 | 8 | 8 | 7 | 7 | 1 | 0 | 7 | 6 | 5 | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186
Note on B3: Minas Kamel: Funsho's: - Auto Allocate - Carbon Reporting
Note on C20: Minas Kamel: Richard?

## Completed Actions
A07 | Confirm Vigo resourcing assumptions remain sufficient | Richard / Jerome | 2026-01-05 | 2026-01-07 | Done
A08 | Brief John Vigo and book design sessions priority LTA then Comparator | Richard | 2026-01-05 | 2026-01-07 | Done
A09 | Re-establish full-team priority alignment session including Vigo | Richard | 2026-01-05 | 2026-01-09 | Done
A10 | Attend NH IFT clarification meeting | Venkatesh | 2026-01-05 | 2026-01-07 08:00 | Done
A11 | Post-IFT impact assessment on timeline | Venkatesh / Richard | 2026-01-05 | 2026-01-08 | Done
A05 | Complete internal UAT execution and issue UAT documentation to Louise | Caroline | 2026-01-05 | 2026-01-06 | Done
A13 | Resolve remaining External UAT P2 defect (Create Project) and confirm retest pass | David / Jerome | 2026-01-06 | 2026-01-07 | Done
A18 | Populate Stage Gate tracker with historic milestones and next-week forecast dates | Richard | 2026-01-06 | 2026-01-07 | Done
A19 | Prepare inputs for SRO pack covering story points | Richard | 2026-01-06 | 2026-01-07 | Done
A22 | Propose and set up weekly unblocker check-in with NH leadership group | Richard | 2026-01-06 | 2026-01-09 | Done
A23 | Document and confirm agreed NH scope reduction (no supplier-specific library) aligned to FRS | Richard | 2026-01-07 | 2026-01-09 | Done
A24 | Review NH clarification meeting recording and confirm scope position to proceed | Minas | 2026-01-07 | 2026-01-07 | Done
A25 | Produce PRD based on confirmed NH scope (post-clarification) | Venkatesh | 2026-01-07 | 2026-01-12 | Done
A29 | Update delivery plan based on Vigo feedback and potential milestone improvements | Richard | 2026-01-07 | 2026-01-09 | Done
A30 | Unblock Inflation epic by confirming PRD assumptions and enabling partial delivery strategy | Minas | 2026-01-07 | 2026-01-14 | Done
A31 | Document individual blockers and owners for Inflation Stories | Minas | 2026-01-07 | 2026-01-09 | Done
A27 | Track NH sign-off for Release 1D following UAT handover | Caroline | 2026-01-07 | 2026-01-26 | Done

## Work Plan V2 (OLD)
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Dev Start | Dev Finish | SG1 | SG2 | SG3 | SG4 | SG5 | SG6 | SG7 | SG8 | SG9 | SG10 | SG11 | SG12 | Epics | Original Estimate | Updated Estimate | Priority | Allocated Team | Team Work Days (7 SP pd) | Team Work Days (8 SP pd) | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | Total
Carbon Resource Library | Venkatesh |  | 2025-12-24 | 2026-01-07 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-26 | √ |  | √ | [10 empty] | 575 | 55 | 1 | Team 1 | 7.8571 | 6.875 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | F | [66 empty] | 7
Carbon Item Library | Venkatesh |  | 2025-12-24 | 2026-01-07 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-30 | √ |  | √ | [11 empty] | 85 | 2 | Team 4 | 12.1429 | 10.625 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [60 empty] | 11
WBS Carbon & Calc | Venkatesh |  | 2025-12-24 | 2026-01-09 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 | 2026-02-02 | 2026-02-13 | √ | [13 empty] | 75 | 4 | Team 4 | 10.7143 | 9.375 | [31 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | UnLk | [46 empty] | 10
Baseline Assumption | Venkatesh |  | 2025-12-24 | 2026-01-09 | 2026-01-16 | N/A | 2026-01-21 | 2026-01-21 | 2026-01-27 | 2026-02-02 | √ | [13 empty] | 40 | 3 | Team 1 | 5.7143 | 5 | [25 empty] | X | X | X | X |  |  | X | F | [59 empty] | 5
EPD | Venkatesh |  | 2025-12-24 | 2026-01-23 | 2026-01-30 | N/A | 2026-02-05 | 2026-02-05 | 2026-02-03 | 2026-02-17 | √ | [13 empty] | 75 | 5 | Team 1 | 10.7143 | 9.375 | [32 empty] | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | F | [44 empty] | 11
Cost to Carbon Library | Venkatesh |  | 2025-12-24 | 2026-01-16 | 2026-01-23 | N/A | 2026-01-30 | 2026-01-30 | 2026-02-18 | 2026-03-05 | √ | [13 empty] | 85 | 7 | Team 1 | 12.1429 | 10.625 | [47 empty] | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [28 empty] | 12
Auto-Allocate | Venkatesh |  | 2025-12-24 | 2026-01-16 | 2026-01-23 | N/A | 2026-01-30 | 2026-01-30 | 2026-02-16 | 2026-02-27 | √ | [13 empty] | 40 | 6 | Team 4 | 5.7143 | 5 | [45 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 10
Carbon Reports | Minas |  | 2026-01-16 | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-06 | 2026-02-12 | 2026-02-18 | [14 empty] | 40 |  | Team 3 | 5.7143 | 5 | [41 empty] | X | X |  |  | X | X | X | F | [43 empty] | 5
Interim Forecasting Tool (incl EPD) | Venkatesh |  | 2026-01-09 | 2026-01-16 | 2026-01-23 | N/A | 2026-01-30 | 2026-01-30 | 2026-01-05 | 2026-03-22 | [12 empty] | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 | 1 | Team 4 | 28.5714 | 25 |  |  |  | X | X | X | X | X |  |  | X | X | X | X | [45 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | F | [9 empty] | 26
Long-Term Appraisal | Minas |  | Fri 12 Dec 2025 | 2026-01-23 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-06 | 2026-01-29 | 2026-03-05 | √ | [11 empty] | VER10-9697, VER10-9698, VER10-9699, VER10-9700, VER10-9701, VER10-9702 | 260 | 180 | 4 | Team 2 | 25.7143 | 22.5 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [28 empty] | 26
Comparator | Minas | Y | Fri 12 Dec 2025 | 2026-01-19 | 2026-01-26 | N/A | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-20 | √ | [11 empty] | VER10-8953 | 120 | 120 | 4 | Team 5 | 17.1429 | 15 | [31 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [39 empty] | 15
Workflow | Minas | Y | Wed 17 Dec 2025 | 2026-01-16 | N/A | 2026-01-20 | 2026-01-26 | 2026-01-26 | 2026-01-29 | 2026-01-26 | √ | [11 empty] | VER10-9028 | 35 | 35 | 5 | Team 3 | 5 | 4.375 | [18 empty] | X | X | X | X |  |  | X | F | [66 empty] | 5
Portfolio/Programme Risk | Minas |  | Fri 12 Dec 2025 | 2025-12-22 | 2026-01-30 | N/A | 2026-02-06 | 2026-02-06 | 2026-02-09 | 2026-02-19 | √ | [11 empty] | VER10-9494 | 80 | 60 | 5 | Team 3 | 8.5714 | 7.5 | [38 empty] | X | X | X | X | X |  |  | X | X | X | F | [43 empty] | 8
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 | 2026-01-09 | N/A | 2026-01-16 | 2026-01-23 | 2026-01-23 | 2026-01-26 | 2026-01-28 | √ | [11 empty] | No Epic | 20 | 20 | 6 | Team 5 | 2.8571 | 2.5 | [24 empty] | X | X | X | F | [64 empty] | 3
Scenario Analysis (Chapter 7) | Minas? (TBC) |  | 2026-01-23 | 2026-01-30 | 2026-02-06 | N/A | 2026-02-13 | 2026-02-13 | 2026-02-23 | 2026-03-12 | [12 empty] | VER10-8958 | 140 | 100 | 5 | Team 3 | 14.2857 | 12.5 | [52 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  |  | X | X | X | F | [21 empty] | 13
Star Rates | Minas? (TBC) |  | 2026-02-06 | 2026-02-11 | N/A | 2026-02-13 | 2026-02-20 | 2026-02-20 | 2026-01-19 | 2026-01-28 | [12 empty] | No Epic | 90 | 60 |  | Team 2 | 8.5714 | 7.5 | [52 empty] | X | X | X | X | X |  |  | X | X | X | F | [29 empty] | 8
TPE | Venkatesh |  | 2026-01-30 | 2026-02-06 | 2026-02-13 | N/A | 2026-02-20 | 2026-02-20 | 2026-02-23 | 2026-03-23 | [12 empty] | VER10-9184 | 350 | 215 | 4 | Team 5 | 30.7143 | 26.875 | [52 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | F | [10 empty] | 21
Dashboards (Power BI) | Minas |  | 2026-01-09 | 2026-01-16 | N/A | N/A | N/A | N/A | 2026-01-19 | 2026-01-23 | [12 empty] | No Epic | 40 | 40 | 2 | Dashboard Team | 5.7143 | 5 | [17 empty] | X | X | X | X | X |  |  | F | [67 empty] | 5
Contractor Fee Library | Minas |  | 2026-01-30 | 2026-02-04 | N/A | 2026-02-11 | 2026-02-18 | 2026-02-18 | 2026-03-06 | 2026-03-18 | [12 empty] | VER10-9271 | 90 | 80 | 3 | Team 2 | 11.4286 | 10 | [63 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [14 empty] | 10
System Access | Minas |  | 2026-02-06 | N/A | N/A | 2026-02-13 | 2026-02-20 | 2026-02-20 | 2026-01-05 | 2026-01-16 | [12 empty] | VER10-8452 | 40 | 40 | 3 | Team 5 | 5.7143 | 5 |  |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [74 empty] | 10
Audit Log | Minas |  | 2026-01-09 | 2026-01-16 | N/A | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-22 | 2026-01-22 | [12 empty] | VER10-8955, VER10-6972 | 10 | 11 |  | Team 5 | 1.5714 | 1.375 | [20 empty] | X | F | [70 empty] | 1
WBS Tags and Custom Fields | Minas |  | Done | Done | Done | Done | Done | Done | 2025-12-01 | 2026-01-09 | √ | √ | √ | √ | √ | √ | [6 empty] | VER10-8916, VER10-8268 | 10 | 10 |  | Team 2 | 1.4286 | 1.25 | [6 empty] | X | F | [84 empty] | 1
Reporting Foundation Admin | Minas |  | Done | Done | Done | Done | Done | Done | 2025-12-04 | 2026-01-09 | √ | √ | √ | √ | √ | √ | [6 empty] | VER10-8476 | 19 | 19 |  | Team 3 | 2.7143 | 2.375 |  |  |  |  | X | X | X | F | [84 empty] | 3
Inflation | Minas |  | Done | Done | Done | Done | Done | Done | 2025-12-04 | 2026-01-16 | √ | √ | √ | √ | √ | √ | [6 empty] | VER10-8903, VER10-8570 | 41 | 41 |  | Team 3 | 5.8571 | 5.125 | [10 empty] | X | X | X | X | X |  |  | F | [74 empty] | 5
AR and O&M fixed reports | Minas |  | Done | Done | Done | Done | Done | Done | 2026-01-09 | 2026-01-16 | √ | √ | √ | √ | √ | √ | [6 empty] | VER10-7878, VER10-7879 | 47 | 47 |  | Team 3 | 6.7143 | 5.875 | [7 empty] | X |  |  | X | X | X | X | X |  |  | F | [74 empty] | 6
CCESS | Minas |  | Done | Done | Done | Done | Done | Done | 2026-02-19 | 2026-02-20 | √ | √ | √ | √ | [8 empty] | VER10-6966 | 5 | 5 |  | Team 3 | 0.71429 | 0.625 | [48 empty] | X | F | [42 empty] | 1
[24 empty] | 2149 | 1778 | 1848 |  | 254 | 222.25 | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 3 | 0 | 0 | 4 | 4 | 4 | 4 | 5 | 0 | 0 | 3 | 4 | 4 | 5 | 4 | 0 | 0 | 4 | 3 | 3 | 3 | 3 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 6 | 6 | 0 | 0 | 6 | 6 | 6 | 5 | 4 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 6 | 6 | 5 | 4 | 0 | 0 | 3 | 4 | 4 | 4 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238
Key | For this week | [25 empty] | Team 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
| Complete | [25 empty] | Team 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
| At risk (Mitigation) | [25 empty] | Team 3 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46
| Blocked | [25 empty] | Team 4 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
[27 empty] | Team 5 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
[27 empty] | Total |  |  | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 3 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 1 | 2 | 2 | 3 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 6 | 6 | 0 | 0 | 6 | 6 | 6 | 5 | 4 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 6 | 6 | 5 | 4 | 0 | 0 | 3 | 4 | 4 | 4 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on H16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Richard Casey marking this one as done since the UI design from the SRS (and Jonny’s POC) is sufficient
Note on C17: Minas Kamel: Richard?

## Weekly 19-Jan
Day | Deliverable / Task | Owner | Stage Gate | RAG | Escalation Request
From Last Week | PRD Review - Cost to Carbon | Richard | SG2 - NH Sign-Off | 2026-01-16 | Was delivered 17-01-2026
| PRD Review - IFT | Richard | SG2 - NH Sign-Off | 2026-01-16 | BES to confirm which IFT PRD needs to be reviewed (1D)
| PRD Review - Auto Allocate | Richard | SG2 - NH Sign-Off | 2026-01-16 | Was delivered 17-01-2026
Monday | Sprint 35 - Day 1 Starts | Richard | None | Done
Friday | PRD - EPD
| SA - Carbon Resource Library | Jerome | SG5 -SA Review | Done
| SA - Carbon Item Library | Jerome | SG5 -SA Review | In Prog
| SA - Import/Export | Jerome | SG5 -SA Review | In Prog
| SA - WBS Carbon Calcs | Jerome | SG5 -SA Review | In Prog
| SA - Cost Models/Calculators | Jerome | SG5 -SA Review | Done
Escalations
Monday | Meeting needed with NH re TPE | Richard |  | In Prog | Setup for Thursday 22nd
| Meeting needed with NH re Scenario Analysis | Richard |  | In Prog | To be scheduled for next week
| Meeting needed with NH re IFT | Richard |  | Done | Setup for Tuesday 20th
Tuesday | Meeting required with NH for LTA | Richard |  | In Prog | Awaiting dates from Ramesh
Weds | Escalation to NH re delay due to missed stage gates

## Weekly 12-Jan
Day | Deliverable / Task | Owner | Stage Gate | RAG | Escalation Request
Monday | Overall Sprint Plan | Richard | No | Done
Tuesday | Detailed Sprint Plan for Sprint 35 | Richard | SG6 - Sprint Planning | Done
| Carbon Item Library | Minas/V | SG2 - NH Sign-Off | Done
| WBS Carbon and Calcs | Minas/V | SG2 - NH Sign-Off | Done
| Baseline Assumption | Minas/V | SG2 - NH Sign-Off | Done
| Calculators and Cost Models | Minas/V | SG2 - NH Sign-Off | Done
| Workflow | Minas/V | SG2 - NH Sign-Off | In Prog | A simpler version to be re-issued - will move into next week - no impact to plan
| EPD | Minas/V | SG1 - PRD Review | Done
Wednesday | Initial Sprint Planning for Sprint 36 | Richard | SG6 - Sprint Planning | Done | Will finalise Thursday
| SA - Carbon Resource Library | Jerome | SG4 - SA Drafted | Done
| SA - Carbon Item Library | Jerome | SG4 - SA Drafted | In Prog
| SA - Import/Export |  |  | In Prog
Thursday | Initial Sprint Planning for Sprint 37 | Richard | SG6 - Sprint Planning | Done
Friday | PRD Review - Cost to Carbon | Richard | SG2 - NH Sign-Off | In Prog
| PRD Review - IFT | Richard | SG2 - NH Sign-Off | In Prog
| PRD Review - Auto Allocate | Richard | SG2 - NH Sign-Off | In Prog
| PRD Draft - Carbon Reports | Minas | SG1 - PRD Draft | In Prog
| SA - Carbon Resource Library | Jerome | SG5 -SA Review | Done
| SA - Carbon Item Library | Jerome | SG5 -SA Review | In Prog

## Weekly 05-Jan
Day | Deliverable / Task | Owner | Stage Gate | RAG | Escalation Request
Monday | Confirm Engineering Team Allocation | Jerome | No | Done
| Confirm Capacity and Resource Level Mapping | Jerome | No | Done
| Send Plan Dates to Vigo for Designs | Richard | No | Done
| External UAT Sanity Checks (R1D) | Caroline | SG8 - QA Complete | Done
Tuesday | Sprint Planning Session 1 for Release 2A | Richard | SG6 - Sprint Planning | In Prog
| Internal UAT Complete (R1D) | Caroline | SG8 - QA Complete | Done
Wednesday | UAT Handover to NH (Release 1D) | Caroline | SG8 - QA Complete | Done
Thursday | Sprint Planning Session 2 for Release 2A | Richard | SG6 - Sprint Planning | In Prog
Friday | Audit Log Released | Minas | SG1 - PRD | Done
| PowerBI Dashboards | Minas | SG1 - PRD | In Prog
| Interim Forecasting Tool | Richard | SG1 - PRD | In Prog | Escalated - Position confirmed and documented, will get NH confirmation in writing
| Carbon Resource Library | Richard | SG2 - NH Sign-Off | Done | Escalted at SRO - was agreed that if the 3 stage gates are met, then it has implicit sign-off
| Carbon Item Library | Richard | SG2 - NH Sign-Off |  | Need to discuss with Mark
| WBS Carbon and Calcs | Richard | SG2 - NH Sign-Off
| Baseline Assumption | Richard | SG2 - NH Sign-Off |  | Need discussion with Mark
| Calculators and Cost Models | Richard | SG2 - NH Sign-Off
| Workflow | Richard | SG2 - NH Sign-Off |  | This will be reworked with a simpler version and a new PRD will be issued
| EPD | Richard | SG2 - NH Sign-Off
| Carbon Resource Library | Richard | SG3 - UX/UI Design | Done
| Carbon Item Library | Richard | SG3 - UX/UI Design | Done