## Full-Delivery
Epic |  | Release | Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33 | Sprint 34 | Sprint 35 | Sprint 36 | Sprint 37 | Sprint 38 | TOTALS
Dates | Lead Team |  | 2025-10-23 | 2025-11-06 | 2025-11-20 | 2025-12-04 | 2025-12-18 | 2026-01-01 | 2026-01-15 | 2026-01-29 | 2026-02-12
VER-6968 - Carbon Rate Application | Team 1 | 1D | 2025-10-23: 18; 2025-11-06: 11; 2025-11-20: 5 | 34
VER-7822 - Estimate Request Revised | Team 1 | 1D | 2025-10-23: 26; 2025-11-06: 5 | 31
VER-8452 - Role Permissions for NH Reviewer and Approvals | Team 1 | 1D | 2025-11-20: 10; 2025-12-04: 10 | 20
VER-9084 - Template Mapping Config | Team 1 | 1D | 2025-12-04: 20 | 20
VER-8473 - Implement Full Custom Fields (WBS) | Team 2 | 1D | 2025-10-23: 27; 2025-11-06: 20; 2025-11-20: 10 | 57
VER-6825 - Tagging and Dimensions (Admin) | Team 3 | 1D | 2025-10-23: 4; 2025-11-06: 0; 2025-11-20: 10 | 14
VER-8474 - Tagging and Dimensions (WBS) | Team 3 | 1D | 2025-10-23: 15; 2025-11-06: 20; 2025-11-20: 10 | 45
VER-8476 - Reporting Foundations (Admin) | Team 3 | 1D | 2025-10-23: 8; 2025-11-06: 10; 2025-11-20: 20 | 38
VER-7425 - Sub-Items Resource in Estimate | Team 4 | 1D | 2025-10-23: 2; 2025-11-06: 2 | 4
VER-7504 - Template Library Browser | Team 4 | 1D | 2025-10-23: 7; 2025-11-06: 2 | 9
VER-8767 - Template Library Admin Roles and Audit | Team 4 | 1D | 2025-10-23: 18; 2025-11-06: 8 | 26
VER-8768 - Template Library CRUD Ops | Team 4 | 1D | 2025-10-23: 19; 2025-11-06: 11 | 30
VER-8758 - Template Library Create Estimate from Templatee | Team 4 | 1D | 2025-10-23: 18; 2025-11-06: 10; 2025-11-20: 15 | 43
VER-8678 - Supply Chain - Forecast Browser | Team 4 | 1D | 2025-12-04: 6 | 6
VER-8680 - Supply Chain - Supplier data entry and submission | Team 4 | 1D | 2025-12-04: 20; 2025-12-18: 20 | 40
VER-8681 - Supply Chain - Data Consolodation and Validation | Team 4 | 1D | 2025-12-18: 10; 2026-01-01: 10 | 20
VER-8682 - Supply Chain - Submit Revision for NH Review | Team 4 | 1D | 2026-01-01: 20 | 20
VER-8858 - Supply Chain - Forecasting Admin Controls | Team 4 | 1D | 2025-11-20: 9 | 9
VER-7936 - Resource Library in WBS (FE Uplift) | Team 4 | 1D | 2025-11-06: 10 | 10
VER-8014 - Implement App-wide changes | Team 5 | 1D | 2025-10-23: 4; 2025-11-06: 10 | 14
VER-8168 - Advanced Quote Numbering | Team 4 | 1D | 2025-10-23: 4; 2025-11-06: 3 | 7
VER-8679 - Supply Chain - Manage Revision | Team 4 | 1D | 2025-12-04: 20 | 20
VER-8921 - Supply Chain - Forecast initiation and distribution | Team 4 | 1D | 2025-11-20: 20; 2025-12-04: 20 | 40
VER-8999 - Standardisation API contract | Team 4 | 1D | 2025-11-06: 5; 2025-11-20: 10 | 15
VER-8953 - Estimate and Control Element Comparator | Team 2 | 2A | 2025-12-18: 10; 2026-01-01: 20; 2026-01-15: 10 | 40
VER-8954 - Carbon Export | Team 2 | 2A | 2025-12-18: 10 | 10
VER-8570 - Inflation - Library Setup and WBS | Team 2 | 2A | 2025-11-20: 15; 2025-12-04: 20; 2025-12-18: 6 | 41
VER-8903 - Inflation Rebasing and Future Inflation | Team 2 | 2A | 2025-12-04: 20; 2025-12-18: 12 | 32
VER-8565 - LTA Estimate Shell and Template | Team 2 | 2A | 2025-12-04: 10; 2025-12-18: 10 | 20
VER-8966 - Estimate Export - Expediture Profile - O&M | Team 3 | 2A | 2025-11-06: 5; 2025-12-18: 5 | 10
VER-7815 - Estimate Export - Expenditure Profile - AR | Team 3 | 2A | 2025-11-06: 5; 2025-12-18: 10; 2026-01-01: 10 | 25
VER-8955 - Audit Log and Traceability | Team 3 | 2A | 2025-12-18: 20; 2026-01-01: 20; 2026-01-15: 20 | 60
VER-7878 - O&M fixed reports | Team 3 | 2A | 2026-01-01: 20; 2026-01-15: 12 | 32
VER-7879 - Asset Renewals Fixed Reports | Team 3 | 2A | 2025-12-04: 7; 2025-12-18: 10; 2026-01-01: 20; 2026-01-15: 10 | 47
VER-8916 - WBS Filtering Tags and Custom Fields | Team 3 | 2A | 2025-11-06: 3 | 3
VER-9028 - Workflow (email/notifications) | Team 3 | 2A | 2026-01-01: 20; 2026-01-15: 20 | 40
VER-9049 - Supply Chain - R2A Scope |  | 2A | 2025-11-20: 20; 2025-12-04: 20; 2025-12-18: 10; 2026-01-01: 20; 2026-01-15: 20 | 90
VER-8959 - EPD |  | 2A | 2026-01-01: 20; 2026-01-15: 20 | 40
VER-8958 - Scenario Analysis |  | 2A | 2025-12-18: 10; 2026-01-01: 20; 2026-01-15: 20 | 50
VER-TBC - Tech Debt |  | 1D | 2025-11-06: 10; 2025-11-20: 20; 2025-12-04: 20 | 50
VER-TBC - Tech Debt |  | 2A | 2025-12-18: 10; 2026-01-01: 20; 2026-01-15: 20 | 50
STABILIZATION |  | STABILIZE | 2025-10-23: 20; 2025-11-06: 25; 2025-11-20: 25; 2025-12-04: 25; 2026-01-01: 25 | 120
BUGS |  | BUGS | 80 | 45 | 20 | 10 | 10 | 20 | 20 | 40 |  | 245
CONTINGENCY |  | CONTING |  | 30 | 20 | 20 | 10 | 20 | 20 | 20 |  | 140
0
TOTAL Committed Story Points Per Sprint |  |  | 270 | 250 | 239 | 248 | 173 | 285 | 192 | 40 | 0
DELIVERED TODAY | 26
Story Points Delivered | ] |  | 2025-10-23: 215; 2025-11-06: 76
SCRIPT IGNORE BELOW HERE
Development |  |  | 2025-10-23: 115
XMAS Week
R1D Total SP | 572
R2A Total SP | 540
Bugs Total | 245
Tech Debt Total | 100
Contingency Total | 140
TOTAL PROJECT REMAING STORY POINTS | 1597

## Progress
Date | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18
Committed Story Points | 12.5 | 17.5 |  |  | 25 | 30 | 32.5 | 47.5 | 30 |  |  | 25 | 17.5 | 12.5 | 13.6 | 19 |  |  | 27.1 | 32.5 | 35.2 | 51.5 | 32.5 |  |  | 27.1 | 19 | 13.6 | 12.4 | 17.4 |  |  | 24.8 | 29.8 | 32.2 | 47.1 | 29.8 |  |  | 24.8 | 17.4 | 12.4 | 8.7
Actual Story Points | 13 | 22 | 3 | 0 | 9 | 19 | 11 | 8 | 4 | 1 | 0 | 10 | 4 | 15 | 6
Cumulative Committed | 12.5 | 30 | 30 | 30 | 55 | 85 | 117.5 | 165 | 195 | 195 | 195 | 220 | 237.5 | 250 | 263.6 | 282.6 | 282.6 | 282.6 | 309.7 | 342.2 | 377.4 | 428.9 | 461.4 | 461.4 | 461.4 | 488.5 | 507.5 | 521.1 | 533.5 | 550.9 | 550.9 | 550.9 | 575.7 | 605.5 | 637.7 | 684.8 | 714.6 | 714.6 | 714.6 | 739.4 | 756.8 | 769.2 | 777.9
Cumulative Actual | [15 empty] | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74
Variance
Burndown | 750 | 732 | 732 | 732 | 714 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695 | 695

## Designs
VER-6968 - Carbon Rate Application | 100%
VER-7822 - Estimate Request Revised | 100%
VER-8452 - Role Permissions for NH Reviewer and Approvals | 100%
VER-9084 - Template Mapping Config
VER-8473 - Implement Full Custom Fields (WBS)
VER-6825 - Tagging and Dimensions (Admin)
VER-8474 - Tagging and Dimensions (WBS)
VER-8476 - Reporting Foundations (Admin)
VER-7425 - Sub-Items Resource in Estimate
VER-7504 - Template Library Browser
VER-8767 - Template Library Admin Roles and Audit
VER-8768 - Template Library CRUD Ops
VER-8758 - Template Library Create Estimate from Templatee
VER-8678 - Supply Chain - Forecast Browser
VER-8680 - Supply Chain - Supplier data entry and submission
VER-8681 - Supply Chain - Data Consolodation and Validation
VER-8682 - Supply Chain - Submit Revision for NH Review
VER-8858 - Supply Chain - Forecasting Admin Controls
VER-7936 - Resource Library in WBS (FE Uplift)
VER-8014 - Implement App-wide changes
VER-8168 - Advanced Quote Numbering
VER-8679 - Supply Chain - Manage Revision
VER-8921 - Supply Chain - Forecast initiation and distribution
VER-8999 - Standardisation API contract
VER-8953 - Estimate and Control Element Comparator
VER-8954 - Carbon Export
VER-8570 - Inflation - Library Setup and WBS
VER-8903 - Inflation Rebasing and Future Inflation
VER-8565 - LTA Estimate Shell and Template
VER-8966 - Estimate Export - Expediture Profile - O&M
VER-7815 - Estimate Export - Expenditure Profile - AR
VER-8955 - Audit Log and Traceability
VER-7878 - O&M fixed reports
VER-7879 - Asset Renewals Fixed Reports
VER-8916 - WBS Filtering Tags and Custom Fields
VER-9028 - Workflow (email/notifications)
VER-9049 - Supply Chain - R2A Scope
VER-8959 - EPD
VER-8958 - Scenario Analysis

## Sprint 30
Epic | 23/10/2025 | 24/10/2025 | 25/10/2025 | 26/10/2025 | 27/10/2025 | 28/10/2025 | 29/10/2025 | 30/10/2025 | 31/10/2025 | 01/11/2025 | 02/11/2025 | 03/11/2025 | 04/11/2025 | 05/11/2025
VER-6968 - Carbon Rate Application | 1.8 | 1.8 |  |  | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 |  |  | 1.8 | 1.8 | 1.8
VER-7822 - Estimate Request Revised | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6
VER-8473 - Implement Full Custom Fields (WBS) | 2.7 | 2.7 |  |  | 2.7 | 2.7 | 2.7 | 2.7 | 2.7 |  |  | 2.7 | 2.7 | 2.7
VER-6825 - Tagging and Dimensions (Admin) | 0.4 | 0.4 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 |  |  | 0.4 | 0.4 | 0.4
VER-8474 - Tagging and Dimensions (WBS) | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5
VER-8476 - Reporting Foundations (Admin) | 0.8 | 0.8 |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  |  | 0.8 | 0.8 | 0.8
VER-7425 - Sub-Items Resource in Estimate | 0.2 | 0.2 |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  |  | 0.2 | 0.2 | 0.2
VER-7504 - Template Library Browser | 0.7 | 0.7 |  |  | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 |  |  | 0.7 | 0.7 | 0.7
VER-8767 - Template Library Admin Roles and Audit | 1.8 | 1.8 |  |  | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 |  |  | 1.8 | 1.8 | 1.8
VER-8768 - Template Library CRUD Ops | 1.9 | 1.9 |  |  | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 |  |  | 1.9 | 1.9 | 1.9
VER-8758 - Template Library Create Estimate from Templatee | 1.8 | 1.8 |  |  | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 |  |  | 1.8 | 1.8 | 1.8
VER-8014 - Implement App-wide changes | 0.4 | 0.4 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 |  |  | 0.4 | 0.4 | 0.4
VER-8168 - Advanced Quote Numbering | 0.4 | 0.4 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 |  |  | 0.4 | 0.4 | 0.4
STABILIZATION | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
BUGS | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8
Story Points Committed | 27 | 27 |  |  | 27 | 27 | 27 | 27 | 27 |  |  | 27 | 27 | 27
Story Points Delivered | 21.5 | 21.5 |  |  | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 |  |  | 21.5 | 21.5 | 21.5
Story Points Remaining
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Remaining
To create burndown chart for Sprint 30:
1. Select the Day and Points Remaining data above
2. Insert > Chart > Line Chart
3. Set chart title to "Burndown for Sprint 30"

## Sprint 31
Epic | 06/11/2025 | 07/11/2025 | 08/11/2025 | 09/11/2025 | 10/11/2025 | 11/11/2025 | 12/11/2025 | 13/11/2025 | 14/11/2025 | 15/11/2025 | 16/11/2025 | 17/11/2025 | 18/11/2025 | 19/11/2025
VER-6968 - Carbon Rate Application | 1.1 | 1.1 |  |  | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 |  |  | 1.1 | 1.1 | 1.1
VER-7822 - Estimate Request Revised | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5
VER-8473 - Implement Full Custom Fields (WBS) | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8474 - Tagging and Dimensions (WBS) | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8476 - Reporting Foundations (Admin) | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-7425 - Sub-Items Resource in Estimate | 0.2 | 0.2 |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  |  | 0.2 | 0.2 | 0.2
VER-7504 - Template Library Browser | 0.2 | 0.2 |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  |  | 0.2 | 0.2 | 0.2
VER-8767 - Template Library Admin Roles and Audit | 0.8 | 0.8 |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  |  | 0.8 | 0.8 | 0.8
VER-8768 - Template Library CRUD Ops | 1.1 | 1.1 |  |  | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 |  |  | 1.1 | 1.1 | 1.1
VER-8758 - Template Library Create Estimate from Templatee | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-7936 - Resource Library in WBS (FE Uplift) | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8014 - Implement App-wide changes | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8168 - Advanced Quote Numbering | 0.3 | 0.3 |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 |  |  | 0.3 | 0.3 | 0.3
VER-8999 - Standardisation API contract | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5
VER-8966 - Estimate Export - Expediture Profile - O&M | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5
VER-7815 - Estimate Export - Expenditure Profile - AR | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5
VER-8916 - WBS Filtering Tags and Custom Fields | 0.3 | 0.3 |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 |  |  | 0.3 | 0.3 | 0.3
VER-TBC - Tech Debt | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
STABILIZATION | 2.5 | 2.5 |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 |  |  | 2.5 | 2.5 | 2.5
BUGS | 4.5 | 4.5 |  |  | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 |  |  | 4.5 | 4.5 | 4.5
CONTINGENCY | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3
Story Points Committed | 25 | 25 |  |  | 25 | 25 | 25 | 25 | 25 |  |  | 25 | 25 | 25
Story Points Delivered | 13 | 22 | 3 | 0 | 9 | 19 | 11 | 8 | 4 | 1 | 0 | 10 | 4 | 15
Story Points Remaining
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Remaining
To create burndown chart for Sprint 31:
1. Select the Day and Points Remaining data above
2. Insert > Chart > Line Chart
3. Set chart title to "Burndown for Sprint 31"

## Sprint 32
Epic | 20/11/2025 | 21/11/2025 | 22/11/2025 | 23/11/2025 | 24/11/2025 | 25/11/2025 | 26/11/2025 | 27/11/2025 | 28/11/2025 | 29/11/2025 | 30/11/2025 | 01/12/2025 | 02/12/2025 | 03/12/2025
VER-6968 - Carbon Rate Application | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5
VER-8452 - Role Permissions for NH Reviewer and Approvals | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8473 - Implement Full Custom Fields (WBS) | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-6825 - Tagging and Dimensions (Admin) | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8474 - Tagging and Dimensions (WBS) | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8476 - Reporting Foundations (Admin) | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8758 - Template Library Create Estimate from Templatee | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5
VER-8858 - Supply Chain - Forecasting Admin Controls | 0.9 | 0.9 |  |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  |  | 0.9 | 0.9 | 0.9
VER-8921 - Supply Chain - Forecast initiation and distribution | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8999 - Standardisation API contract | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8570 - Inflation - Library Setup and WBS | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5
VER-9049 - Supply Chain - R2A Scope | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-TBC - Tech Debt | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
STABILIZATION | 2.5 | 2.5 |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 |  |  | 2.5 | 2.5 | 2.5
BUGS | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
CONTINGENCY | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
Story Points Committed | 23.9 | 23.9 |  |  | 23.9 | 23.9 | 23.9 | 23.9 | 23.9 |  |  | 23.9 | 23.9 | 23.9
Story Points Delivered | 6
Story Points Remaining
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Remaining
To create burndown chart for Sprint 32:
1. Select the Day and Points Remaining data above
2. Insert > Chart > Line Chart
3. Set chart title to "Burndown for Sprint 32"

## Sprint 33
Epic | 04/12/2025 | 05/12/2025 | 06/12/2025 | 07/12/2025 | 08/12/2025 | 09/12/2025 | 10/12/2025 | 11/12/2025 | 12/12/2025 | 13/12/2025 | 14/12/2025 | 15/12/2025 | 16/12/2025 | 17/12/2025
VER-8452 - Role Permissions for NH Reviewer and Approvals | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-9084 - Template Mapping Config | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8678 - Supply Chain - Forecast Browser | 0.6 | 0.6 |  |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 |  |  | 0.6 | 0.6 | 0.6
VER-8680 - Supply Chain - Supplier data entry and submission | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8679 - Supply Chain - Manage Revision | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8921 - Supply Chain - Forecast initiation and distribution | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8570 - Inflation - Library Setup and WBS | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8903 - Inflation Rebasing and Future Inflation | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8565 - LTA Estimate Shell and Template | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-7879 - Asset Renewals Fixed Reports | 0.7 | 0.7 |  |  | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 |  |  | 0.7 | 0.7 | 0.7
VER-9049 - Supply Chain - R2A Scope | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-TBC - Tech Debt | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
STABILIZATION | 2.5 | 2.5 |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 |  |  | 2.5 | 2.5 | 2.5
BUGS | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
CONTINGENCY | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
Story Points Committed | 24.8 | 24.8 |  |  | 24.8 | 24.8 | 24.8 | 24.8 | 24.8 |  |  | 24.8 | 24.8 | 24.8
Story Points Delivered
Story Points Remaining
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Remaining
To create burndown chart for Sprint 33:
1. Select the Day and Points Remaining data above
2. Insert > Chart > Line Chart
3. Set chart title to "Burndown for Sprint 33"

## Sprint 34
Epic | 18/12/2025 | 19/12/2025 | 20/12/2025 | 21/12/2025 | 22/12/2025 | 23/12/2025 | 24/12/2025 | 25/12/2025 | 26/12/2025 | 27/12/2025 | 28/12/2025 | 29/12/2025 | 30/12/2025 | 31/12/2025
VER-8680 - Supply Chain - Supplier data entry and submission | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8681 - Supply Chain - Data Consolodation and Validation | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8953 - Estimate and Control Element Comparator | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8954 - Carbon Export | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8570 - Inflation - Library Setup and WBS | 0.6 | 0.6 |  |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 |  |  | 0.6 | 0.6 | 0.6
VER-8903 - Inflation Rebasing and Future Inflation | 1.2 | 1.2 |  |  | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 |  |  | 1.2 | 1.2 | 1.2
VER-8565 - LTA Estimate Shell and Template | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8966 - Estimate Export - Expediture Profile - O&M | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5
VER-7815 - Estimate Export - Expenditure Profile - AR | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8955 - Audit Log and Traceability | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-7879 - Asset Renewals Fixed Reports | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-9049 - Supply Chain - R2A Scope | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8958 - Scenario Analysis | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-TBC - Tech Debt | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
BUGS | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
CONTINGENCY | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
Story Points Committed | 17.3 | 17.3 |  |  | 17.3 | 17.3 | 17.3 | 17.3 | 17.3 |  |  | 17.3 | 17.3 | 17.3
Story Points Delivered
Story Points Remaining
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Remaining
To create burndown chart for Sprint 34:
1. Select the Day and Points Remaining data above
2. Insert > Chart > Line Chart
3. Set chart title to "Burndown for Sprint 34"

## Sprint 35
Epic | 01/01/2026 | 02/01/2026 | 03/01/2026 | 04/01/2026 | 05/01/2026 | 06/01/2026 | 07/01/2026 | 08/01/2026 | 09/01/2026 | 10/01/2026 | 11/01/2026 | 12/01/2026 | 13/01/2026 | 14/01/2026
VER-8681 - Supply Chain - Data Consolodation and Validation | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8682 - Supply Chain - Submit Revision for NH Review | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8953 - Estimate and Control Element Comparator | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-7815 - Estimate Export - Expenditure Profile - AR | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8955 - Audit Log and Traceability | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-7878 - O&M fixed reports | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-7879 - Asset Renewals Fixed Reports | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-9028 - Workflow (email/notifications) | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-9049 - Supply Chain - R2A Scope | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8959 - EPD | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8958 - Scenario Analysis | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-TBC - Tech Debt | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
STABILIZATION | 2.5 | 2.5 |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 |  |  | 2.5 | 2.5 | 2.5
BUGS | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
CONTINGENCY | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
Story Points Committed | 28.5 | 28.5 |  |  | 28.5 | 28.5 | 28.5 | 28.5 | 28.5 |  |  | 28.5 | 28.5 | 28.5
Story Points Delivered
Story Points Remaining
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Remaining
To create burndown chart for Sprint 35:
1. Select the Day and Points Remaining data above
2. Insert > Chart > Line Chart
3. Set chart title to "Burndown for Sprint 35"

## Sprint 36
Epic | 15/01/2026 | 16/01/2026 | 17/01/2026 | 18/01/2026 | 19/01/2026 | 20/01/2026 | 21/01/2026 | 22/01/2026 | 23/01/2026 | 24/01/2026 | 25/01/2026 | 26/01/2026 | 27/01/2026 | 28/01/2026
VER-8953 - Estimate and Control Element Comparator | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-8955 - Audit Log and Traceability | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-7878 - O&M fixed reports | 1.2 | 1.2 |  |  | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 |  |  | 1.2 | 1.2 | 1.2
VER-7879 - Asset Renewals Fixed Reports | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1
VER-9028 - Workflow (email/notifications) | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-9049 - Supply Chain - R2A Scope | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8959 - EPD | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-8958 - Scenario Analysis | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
VER-TBC - Tech Debt | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
BUGS | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
CONTINGENCY | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
Story Points Committed | 19.2 | 19.2 |  |  | 19.2 | 19.2 | 19.2 | 19.2 | 19.2 |  |  | 19.2 | 19.2 | 19.2
Story Points Delivered
Story Points Remaining
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Remaining
To create burndown chart for Sprint 36:
1. Select the Day and Points Remaining data above
2. Insert > Chart > Line Chart
3. Set chart title to "Burndown for Sprint 36"

## Sprint 37
Epic | 29/01/2026 | 30/01/2026 | 31/01/2026 | 01/02/2026 | 02/02/2026 | 03/02/2026 | 04/02/2026 | 05/02/2026 | 06/02/2026 | 07/02/2026 | 08/02/2026 | 09/02/2026 | 10/02/2026 | 11/02/2026
BUGS | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4
CONTINGENCY | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
Story Points Committed | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6
Story Points Delivered
Story Points Remaining
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Remaining
To create burndown chart for Sprint 37:
1. Select the Day and Points Remaining data above
2. Insert > Chart > Line Chart
3. Set chart title to "Burndown for Sprint 37"

## Sprint 38
Epic | 12/02/2026 | 13/02/2026 | 14/02/2026 | 15/02/2026 | 16/02/2026 | 17/02/2026 | 18/02/2026 | 19/02/2026 | 20/02/2026 | 21/02/2026 | 22/02/2026 | 23/02/2026 | 24/02/2026 | 25/02/2026
Story Points Committed
Story Points Delivered
Story Points Remaining
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Remaining
To create burndown chart for Sprint 38:
1. Select the Day and Points Remaining data above
2. Insert > Chart > Line Chart
3. Set chart title to "Burndown for Sprint 38"