## Work Plan - Review SP (WIP)
Design Due Dates
Workstream | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Due Date | Epics | Story Point Estimate for Dev |  | Assumed Estimate | Team Days (current 25SP/d)
Estimate Build – Carbon | Venkatesh & Funsho |  | 46015 | 46021 | 46038 | N/A | 46045 | 46045 | VER10-8954, VER10-9428, VER10-9464, VER10-9527, VER10-9523 | 575 | 414 |  | 141.2857
Interim Forecasting Tool | Venkatesh |  | 46031 | 46035 | 46043 | N/A | 46050 | 46050 | VER10-8678, VER10-8680, VER10-8682, VER10-8858,, VER10-8679, VER10-8921, VER10-9049,, VER10-9128, | 177 | 200 |  | 53.8571
Long-Term Appraisal | Funsho |  | Fri 12 Dec 2025 (Done on time) | 46008 | 46037 | N/A | 46044 | 46044 | VER10-8565 | 260 | 200 |  | 65.7143
Comparator | Funsho | Y | 19/12/2025 (Done on time) | 46015 | 46037 | N/A | 46044 | 46044 | VER10-8953 | 120 | 100 |  | 31.4286
Workflow | Funsho | Y | Wed 17 Dec 2025 (1 day delay) | 46010 | N/A | 46031 | 46038 | 46038 | VER10-9028 | 35 | 35 |  | 10
Tasks | Funsho |  | Wed 17 Dec 2025 (1 day delay) | 46010 | N/A | 46031 | 46038 | 46038 | VER10-9027 | 40 | 0 |  | 5.7143
Portfolio/Programme Risk | Funsho |  | Fri 12 Dec 2025 (Done on time) | 46008 | 46044 | N/A | 46051 | 46051 | VER10-9494 | 80 | 60 |  | 20
Calculators/Cost Models (Chapter 10) | Minas |  | Thu 18 Dec 2025 (Done on time) | 46015 | N/A | 46031 | 46038 | 46038 | No Epic | 20 | 20 |  | 5.7143
Scenario Analysis (Chapter 7) | Venkatesh? (TBC) |  | Fri, 13 Feb 2026 | Fri, 20 Feb 2026 | 46051 | N/A | 46058 | 46058 | VER10-8958 | 140 | 100 |  | 34.2857
Star Rates | Minas? (TBC) |  | 46045 | 46052 | N/A | 46059 | 46066 | 46066 | No Epic | 90 | 60 |  | 21.4286
TPE | Venkatesh |  | 46045 | 46050 | 46059 | N/A | 46066 | 46066 | VER10-9184 | 350 | 215 |  | 80.7143
Dashboards (Power BI) | Minas |  | 46015 | 46022 | 46051 | N/A | 46058 | 46058 | No Epic | 40 | 40 |  | 11.4286
Contractor Fee Library | Minas |  | 46031 | 46036 | N/A | 46038 | 46045 | 46045 | VER10-9271 | 90 | 80 |  | 24.2857
System Access | Minas |  | 46038 | N/A | N/A | 46038 | 46045 | 46045 | No Epic | 40 | 40 |  | 11.4286
Audit Log | Minas |  | 46052 | 46059 | N/A | 46066 | ? |  | VER10-8955 | 10 | 11 |  | 3
WBS Tags and Custom Fields | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8916, VER10-8268 | Need Estimate | Need Estimate |  | 0
Reporting Foundation Admin | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8476 | 19 | 19 |  | 5.4286
Inflation | Funsho |  | Done | Done | Done | Done | Done | Done | VER10-8903, VER10-8570 | 41 | 41 |  | 11.7143
AR and O&M fixed reports |  |  | Done | Done | Done | Done | Done | Done | VER10-7878, VER10-7879 | 47 | 47 |  | 13.4286
CCESS |  |  | Done | Done | Done | Done | Done | Done | VER10-6966 | 5 | 5 |  | 1.4286
[10 empty] | 2179 | 1687 |  | 552.2857

## Capacity
|  | per week | whole team
Required per team per day | 7 | 35 | 175
Ideal per team per day | 8 | 40 | 200
per dev per day |  | 1.4286

## Teams Allocation
| # points / week | 46013 | 46020 | 45662 | 45669 | 45676 | 45683 | 45690 | 45697 | 45704 | 45711 | 45718 | 45725 | 45732 | 45739
Team 1 Venkatesh & Sunjeet (3 devs) | 25 | [12 empty] | Regression/UAT | UAT
Team 2 Minas & Manish (3 devs) | 25
Team 3 Minas & Vivek (2 devs) | 20
Team 4 Venkatesh & Amit (4 devs) | 30
Team 5 Minas & Laurence (2 devs) | 25
TOTAL | 125
To deliver 1500 points (weeks) | 12
To deliver 1500 points in 9 weeks (SP per week) | 166.6667
Team | Epic | Reduced Estimate | # weeks | Dependent On | Extra Weeks
Team 1 Venkatesh & Sunjeet | Carbon (incl EPD, Auto Allocate) | 455 | 18.2 |  | 6.2
| Carbon Resource Library | 55 | 2.2
| Carbon Item Library | 85 | 3.4 | Carbon Resource
| WBS Carbon & Calc | 75 | 3 | Carbon Libraries
| Baseline Assumption | 40 | 1.6
| EPD | 75 | 3
| Cost to Carbon Library | 85 | 3.4 | Carbon WBS
| Auto-Allocate | 40 | 1.6 | Carbon Libraries
| Carbon Reports | - | -
Team 2 Minas & Manish | Inflation | 41 | 1.64 |  | 2.44
| LTA | 180 | 7.2 | Carbon WBS
| Star Rates | 60 | 2.4
| Contractor Fee Library | 80 | 3.2 | IFT?
Team 3 Minas & Vivek | Reporting Foundation Admin | 19 | 0.95 |  | -1.7
| Portfolio/Programme Risk | 60 | 3
| AR and O&M fixed reports | 47 | 2.35 | Carbon & Reporting Foundation Admin
| CCESS | 5 | 0.25 | Carbon & Reporting Foundation Admin
| Carbon Reports | 40 | 2 | Carbon
| Workflow | 35 | 1.75
Team 4 Venkatesh & Amit | Supply Chain - Interim Forecasting Tool | 200 | 6.6667 | Carbon WBS | 1.8333
| TPE | 215 | 7.1667
Team 5 Minas & Laurence | Audit Log | 11 | 0.44 |  | -0.36
| System Access | 40 | 1.6
| Calculators/Cost Models | 20 | 0.8
| Comparator | 120 | 4.8 | Carbon WBS
| Scenario Analysis | 100 | 4 | Comparator
Work Streams |  | Reduced Estimate | Team
Dashboards (Power BI) |  | 40 | Jonny?
WBS Tags and Custom Fields |  | Need Estimate | ?
Note on C1: Minas Kamel: Assumption: Teams do 25 points a day
Note on C12: Minas Kamel: Funsho's: - Auto Allocate - Carbon Reporting

## MVP Meetings
Topic | Owner | Meeting (UK timezone) | Meeting (AU timezone) | Notes
EPD/Cost to Carbon Factor | Venkatesh | Tue 23rd Dec 10PM-11PM | Wed 24th Dec 9AM-10AM | Meeting done
LTA | Minas | Wed 24th Dec 8AM-9:30AM | Wed24th Dec 7PM-8:30PM | Meeting done
TPE & Auto Allocate (Cost & Carbon) | Venkatesh | Sun 28th Dec 10PM-11:30PM | Mon 29th Dec 9AM-10:30AM | Meeting done
Scenario Analysis (Chapter 7) | Minas | Mon 29th Dec 7AM-8:30AM | Mon 29th Dec 6PM-7:30PM
Carbon Reports | Minas
Supply Chain - Interim Forecasting Tool (incl EPD) | Venkatesh | N/A | N/A | Venkatesh needs meeting with NH
Dashboards (Power BI) | Minas
Comparator | Minas
Workflow | Minas
Tasks | Minas
Calculators/Cost Models (Chapter 10) | Minas
Star Rates | Minas
Contractor Fee Library | Minas
|  | UK | AU | Status | Topic
Mark's avail. |  | Wed 24th Dec UK morning | Wed 24th AU evening | Taken | LTA
|  | Sat 27th Dec 7AM-9AM | Sat 27th Dec 6PM-8PM | X
|  | Sun 28th Dec 7AM-9AM | Sun 28th Dec 6PM-8PM | X
|  | Sun 28th Dec 10PM-11:30PM | Mon 29th Dec 9AM-10:30AM | Taken | TPE & Auto Allocate (Cost & Carbon)
|  | Mon 29th Dec 7AM-9AM | Mon 29th Dec 6PM-8PM | Taken | Scenario Analysis (Chapter 7)
|  | Mon 29th Dec 10PM-11:30PM | Tue 30th Dec 9AM-10:30AM | After MVP deadline (Mon 29th)
|  | Fri 2nd Jan UK morning | Fri 2nd Jan AU evening | After MVP deadline (Mon 29th)

## Action Log
ID | Action | Owner | Raised Date | Due Date / RAG | Status
A06 | Finalise onboarding plan for 4 additional engineers chase profiles and shortlist | Jerome | 46027 | 46031 | In progress
A26 | Continue monitoring NH PRD sign-off behaviour and flag governance risk early | Richard | 46029 | Ongoing | Open
A32 | Risk around TPE and the amount if work to be done in the last Sprint | Richard/Jerome | 46068 | 46068 | In progress
A33 | Capacity / Velocity Concerns | Richard/Jerome | 46068 | 46068 | In progress

## Current Defects
Condition |  |  | Status
P1 > 0 |  |  | 🔴 Escalation
P1 = 0 AND Open defects ↑ for 2+ days |  |  | 🟠 Watch
Open defects ↓ OR steady & closures happening |  |  | 🟢 Stable
Release 1D | [5 empty] | Release 2A
Date | Raised by NH | No P1's | Total Open Defects | Total Closed Today | Daily Status | Date | No P1's | Total No Defects | Total Closed Today | Daily Status
14/01/2026 | 0 | 0 | 27 | 2 | 🟢 Stable | 14/01/2026
15/01/2026 | 0 | 0 | 27 | 0 | 🟢 Stable | 15/01/2026 | 0 | 0 | 0 | 🟢 Stable
16/01/2026 | 0 | 0 | 24 | 3 | 🟢 Stable | 16/01/2026 | 0 | 0 | 0 | 🟢 Stable
17/01/2026 | [5 empty] | 17/01/2026
18/01/2026 | [5 empty] | 18/01/2026
19/01/2026 | 0 | 0 | 23 | 1 | 🟢 Stable | 19/01/2026 | 0 | 0 | 0 | 🟢 Stable
20/01/2026 | 0 | 0 | 18 | 5 | 🟢 Stable | 20/01/2026 | 0 | 0 | 0 | 🟢 Stable
21/01/2026 | 0 | 0 | 16 | 2 | 🟢 Stable | 21/01/2026 | 0 | 0 | 0 | 🟢 Stable
22/01/2026 | 0 | 0 | 15 | 1 | 🟢 Stable | 22/01/2026 | 0 | 0 | 0 | 🟢 Stable
23/01/2026 | 0 | 0 | 13 | 0 | 🟢 Stable | 23/01/2026 | 0 | 0 | 0 | 🟢 Stable
24/01/2026 | [5 empty] | 24/01/2026
25/01/2026 | [5 empty] | 25/01/2026
26/01/2026 | 0 | 0 | 13 | 0 | 🟢 Stable | 26/01/2026 | 0 | 0 | 0 | 🟢 Stable
27/01/2026 | TBC | 0 | 11 | 2 | 🟢 Stable | 27/01/2026 | 0 | 0 | 0 | 🟢 Stable
28/01/2026 | [5 empty] | 28/01/2026
29/01/2026 | [5 empty] | 29/01/2026
30/01/2026 | [5 empty] | 30/01/2026
31/01/2026 | [5 empty] | 31/01/2026
01/02/2026 | [5 empty] | 01/02/2026
Master R1D Defect View - BMJIRA

## stage
Gate | Owner | Rationale | Pass Criteria (Evidence Required) | sheet-col
SCOPE REFINEMENT
1. Individual PRDs Drafted | Minas | Ensures scope and requirements are explicit before design and build begin, avoiding downstream rework and ambiguity. |  | F
|  |  | • PRDs drafted for each of the MVP epics | F
|  |  | • Functional requirements prioritised (Must / Should / Deferred) | F
|  |  | • In-scope vs out-of-scope clearly defined | F
|  |  | • Dependencies and assumptions explicitly documented | F
|  |  | • Dates associated with each of the following Gates are confirmed and committed | F
2A. PRDs Reviewed & Signed Off (NH) | Richard | Confirms shared understanding and agreement with NH to prevent late scope disputes or rework. | • NH review completed | G
|  |  | • Explicit NH sign-off received | G
|  |  | • No open scope alignment questions | G
|  |  | • Any gaps documented, escalated and resolved | G
2B - PRD Hand-off to SA | Minas | Ensure that the full scope and implications of the PRD are understood | All questions raised by Vigo/Design and SA are documented and formally resolved. | G
|  |  | No 'to be clarified' items to remain open unless escalated and approved. | G
|  |  | Vigo and SA have confirmed in writing that the solution is technically coherent and feasible | G
|  |  | Confirmation of the timeline | G
DESIGN STAGES
3. UX/UI Designs Completed | Richard (coordination) | Prevents design churn during development and ensures build teams are working from stable designs. | • UX/UI designs completed for all in-scope MVP flows | H
|  |  | • Designs reviewed and accepted internally | H
|  |  | • Ownership agreed (Vigo vs in-house) | H
|  |  | • No critical design work outstanding for sprint execution | H
4. Solution Architectures (SAs) Drafted | Richard (coordination) | Grounds delivery commitments in technical reality and surfaces assumptions, risks, and trade-offs early. | • SAs drafted for each epic | I
|  |  | • Architecture simplified to MVP | I
|  |  | • Technical assumptions and risks explicit | I
|  |  | • Key trade-offs documented | I
5. SAs Reviewed & Approved | Jerome | Locks technical feasibility before commitments are made and avoids late architectural rework. | • SAs reviewed and approved | J
|  |  | • Risks accepted or mitigated | J
|  |  | • No unresolved feasibility questions | J
|  |  | • Delivery implications understood by Delivery Manager | J
|  |  | • All the required Jira tickets have been reviewed and align with the SA The dates committed, as well as assumptions and effort estimate made in Gate 1, remain valid | J
6. Performance-Aware Design Approved | Yoong | Ensures design and architectural decisions do not inherently introduce performance, scalability, or data-related risk. | • NFR defined (SLOs, throughput, user capacity)
• Scalability expectations, complexity and data volume projections documented
• Database schema optimised with indexing strategy
• APIs follows performance best practices
SPRINT SCHEDULING
5 | Richard | Ensures execution commitments are realistic, capacity-aligned, and dependency-aware before development starts. | • Sprint plan complete by epic
• Scope aligned to PRDs, UX/UI, and SAs
• Dependencies explicit
• Capacity and story points validated
EXECUTION / DELIVERY
8. Development Complete & Code Integrated | Richard | Confirms committed sprint scope is fully built and integrated into the shared codebase, ready for formal QA/system testing. | • All committed stories meet Definition of Done
• Code merged to agreed branch with peer reviews completed
• Sprint review completed and recorded
• Integration complete across in-scope components
• No gating integration issues preventing QA execution
9. System/QA Testing Completed | Owner: Hema Oversight: Caroline | Purpose: Validates functional correctness, system stability, and regression safety prior to Internal and NH UAT. Exit Evidence: QA summary report, defect status, QA sign-off | • Unit testing completed for all in-scope BE/FE components
• Full regression testing executed: • All epics deployed to Regression • End-to-end regression pass completed (≈ 5 days) • Deployment approach confirmed with Dev teams (Yoong)
• Defect position agreed: • Critical / High defects resolved, or • Explicitly accepted with documented risk and approval
• QA Test Summary Report completed and shared (Hema)
• Formal QA sign-off provided (Hema, with Caroline review)
10. Platform Performance & System Readiness Approved Dependencies / risks: Observability capability requires build-out | Yoong | Purpose: Confirms the system can safely operate at expected scale without unacceptable performance, stability, or reliability risk. Exit Evidence: Performance results, monitoring confirmation, readiness sign-off | • Data Load & Scale – Performance and load tests executed – Results conform to agreed thresholds (capacity headroom, error rate) – Estimated duration: 2–3 days
• Regression Protection – No performance degradation beyond agreed threshold (≤5%)
• Observability & Recovery – Monitoring and alerting operational – Logging and diagnostics available to support UAT defect triage – Recovery / rollback approach defined
11. DevOps Deployment to UAT | Jerome | Ensures the solution is correctly deployed, configured, and stable in the UAT environment. QA sign-off (Stage 9) Platform readiness approval (Stage 10) | • Successful deployment to UAT completed – Deployment executed from approved code baseline – Known risk: data-related challenges (tracked and communicated)
• Environment configuration validated – Feature flags, config values, integrations aligned to release scope
• Monitoring, logging, and rollback in place
• Release notes shared with Internal UAT
12. Internal UAT | Caroline | Validates end-to-end functionality, stability, and UAT readiness through internal scenario execution, defect triage, and stakeholder artefact preparation prior to NH business testing. Exit evidence: Internal UAT status, defect summary, readiness confirmation | • Internal UAT execution completed for all in-scope scenarios
• Defects triaged and dispositioned (fix / defer / accept)
• External UAT environment confirmed ready
• Demo recording completed for NH
• Training documentation completed and internally reviewed for NH
• Release notes, training docs and demo shared with NH UAT stakeholders
13. NH UAT Completed & Accepted | Caroline | Confirms solution meets business needs and is approved for production readiness. Outcome: Release approved for onward promotion (subject to programme governance) | • UAT scenarios executed for all in-scope flows
• Business acceptance criteria met
• No unresolved critical/high UAT defects
• Formal UAT sign-off received

## Work Plan V3
|  |  |  | Design Due Dates | [56 empty] | Sprint 36 | [13 empty] | Sprint 37 | [13 empty] | Sprint 38
Workstream | Epics | Owner | NH upfront clarifcation needed? | PRD (sent to NH for review) | NH Sign Off | VIGO: UI/UX Design | Internal: UI/UX Design | SA (Technical Solution Design) | All Design Activities Complete and Tickets Ready | Dev Start | Dev Finish | SG1 | SG2 | SG3 | SG4 | SG5 | SG6 | SG7 | SG8 | SG9 | SG10 | SG11 | SG12 | Original Estimate | Updated Estimate | Priority | Allocated Team | Team Work Days (7 SP pd) | Team Work Days (8 SP pd) | 46024 | 46025 | 46026 | 46027 | 46028 | 46029 | 46030 | 46031 | 46032 | 46033 | 46034 | 46035 | 46036 | 46037 | 46038 | 46039 | 46040 | 46041 | 46042 | 46043 | 46044 | 46045 | 46046 | 46047 | 46048 | 46049 | 46050 | 46051 | 46052 | 46053 | 46054 | 46055 | 46056 | 46057 | 46058 | 46059 | 46060 | 46061 | 46062 | 46063 | 46064 | 46065 | 46066 | 46067 | 46068 | 46069 | 46070 | 46071 | 46072 | 46073 | 46074 | 46075 | 46076 | 46077 | 46078 | 46079 | 46080 | 46081 | 46082 | 46083 | 46084 | 46085 | 46086 | 46087 | 46088 | 46089 | 46090 | 46091 | 46092 | 46093 | 46094 | 46095 | 46096 | 46097 | 46098 | 46099 | 46100 | 46101 | 46102 | 46103 | 46104 | 46105 | 46106 | 46107 | 46108 | 46109 | 46109 | 46110 | 46111 | 46112 | 46113 | 46114 | Total
Carbon Resource Library | VER10-9428, VER10-9464, | Venkatesh / Sanjeet |  | 46015 | 46029 | 46031 | N/A | 46038 | 46038 | Sprint 35 | Sprint 36 | [12 empty] | 575 | 55 | 1 | Team 1 | 7.8571 | 6.875 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | [65 empty] | 9 | bar: SG1 to SG7
Carbon Item Library | VER10-9373, VER10-9826, VER10-9830, VER10-9834 | Venkatesh / Amit S. |  | 46015 | 46029 | 46031 | N/A | 46038 | 46038 | Sprint 35 | Sprint 35 | [13 empty] | 85 | 2 | Team 4 | 12.1429 | 10.625 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 11 | bar: SG1 to SG7
Import / Export | VER10-9874,VER10-9885,VER10-9890, VER10-9893 | Venkatesh / Vivek |  | 46015 | 46029 | 46031 | N/A | 46038 | 46038 | Sprint 35 | Sprint 35 | [15 empty] | Team 3 | [16 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | bar: SG1 to SG7
WBS Carbon & Calc | VER10-9523, VER10-10103, VER10-10106, | Venkatesh / Amit S. Yoong |  | 46015 | 46031 | 46052 | N/A | 46066 | 46069 | Sprint 37 | Sprint 37 | [13 empty] | 75 | 4 | Team 4 | 10.7143 | 9.375 | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 11 | bar: SG1 to SG3
EPD | VER10-8959 | Venkatesh / Sanjeet Amit D. / Yoong |  | 46015 | 46045 | 46064 | N/A | 46070 | 46072 | Sprint 37 | Sprint 37 | [13 empty] | 75 | 5 | Team 1 | 10.7143 | 9.375 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | F | [29 empty] | 14 | bar: SG1
Cost to Carbon Library | VER10-9527, VER10-10135, VER10-10139, VER10-10144 | Venkatesh / Sanjeet |  | 46015 | 46045 | 46046 | N/A | 46069 | 46069 | Sprint 37 | Sprint 38 | [13 empty] | 85 | 7 | Team 1 | 12.1429 | 10.625 | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 11 | bar: SG1 to SG2
Auto-Allocate | NOT NEEDED | Venkatesh / Amit S |  | 46015 | 46045 | 46064 | N/A | 46066 | 46066 | Sprint 37 | Sprint 37 | [13 empty] | 40 | 6 | Team 4 | 5.7143 | 5 | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 11 | bar: SG1
IFT - Dynamic Library | VER10-8678, VER10-8680, VER10-8682, VER10-8858, VER10-8679, VER10-8921, VER10-9049, VER10-9128 | Venkatesh / Amit S / David |  | Fri 12 Dec 2025 | 46045 | 46064 | N/A | 46078 | 46080 | Sprint 35 | Sprint 39 | [12 empty] | 177 | 200 | 1 | Team 4 | 28.5714 | 25 |  |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 40 | bar: SG1 to SG7
IFT - Project Specific Library | VER10-8678, VER10-8680, VER10-8682, VER10-8858, VER10-8679, VER10-8921, VER10-9049, VER10-9128 | Venkatesh / Amit S / David |  | Fri 12 Dec 2025 | 46045 | 46073 | N/A | 46076 | 46079 | Sprint 35 | Sprint 39 | [12 empty] | 177 | 200 | 1 | Team 4 | 28.5714 | 25 |  |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 40 | bar: SG1 to SG7
LTA - Epic 1/2 - RfE + Shell (Entry Point) | VER10-9697, VER10-9698, VER10-9699, VER10-9700, VER10-9701, VER10-9702 | Minas / Manish Ram / David |  | Fri 12 Dec 2025 | 46045 | 46057 | N/A | 46073 | 46069 | Sprint 37 | Sprint 37 | [12 empty] | 260 | 180 | 4 | Team 2 | 25.7143 | 22.5 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | F | [37 empty] | 19 | bar: SG1 to SG2
LTA - Epic 3 - Asset Library | VER10-9697, VER10-9698, VER10-9699, VER10-9700, VER10-9701, VER10-9702 | Minas / Manish Ram / David |  | Fri 12 Dec 2025 | 46045 | 46057 | N/A | 46069 | 46069 | Sprint 38 | Sprint 38 | [12 empty] | 260 | 180 | 4 | Team 2 | 25.7143 | 22.5 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | F | [37 empty] | 19 | bar: SG1 to SG2
LTA - Epic 4/6 - Data Entry & WBS | VER10-9697, VER10-9698, VER10-9699, VER10-9700, VER10-9701, VER10-9702 | Minas / Manish Ram / David |  | Fri 12 Dec 2025 | 46045 | 46057 | N/A | 46073 | 46076 | Sprint 38 | Sprint 38 | [12 empty] | 260 | 180 | 4 | Team 2 | 25.7143 | 22.5 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | F | [37 empty] | 19 | bar: SG1 to SG2
LTA - Epic 5 Annual Profiling | VER10-9697, VER10-9698, VER10-9699, VER10-9700, VER10-9701, VER10-9702 | Minas / Manish Ram / David |  | Fri 12 Dec 2025 | 46045 | 46057 | N/A | 46073 | 46076 | Sprint 37 | Sprint 37 | [12 empty] | 260 | 180 | 4 | Team 2 | 25.7143 | 22.5 | [27 empty] | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | F | [37 empty] | 19 | bar: SG1 to SG2
Comparator | VER10-8953 | Minas / Laurence David | Y | Fri 12 Dec 2025 | 46041 | 46062 | N/A | 46066 | 46069 | Sprint 37 | Sprint 38 | [12 empty] | 120 | 120 | 4 | Team 5 | 17.1429 | 15 | [31 empty] | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [35 empty] | 19 | bar: SG1 to SG2
Carbon Reports |  | Minas / Vivek / Yoong |  | 46031 | 46038 | N/A | N/A | 46073 | 46077 | Sprint 37 | Sprint 38 | [13 empty] | 40 |  | Team 3 | 5.7143 | 5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [35 empty] | 10
Estimate Workflow (Reviewal, Approval, Issuing) | VER10-9028 | Minas / Vivek | Y | Fri 12 Dec 2025 | 46052 | 46069 | N/A | 46076 | 46076 | Sprint 38 | Sprint 38 | [12 empty] | 35 | 35 | 5 | Team 3 | 5 | 4.375 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 11 | bar: SG1
Portfolio/Programme Risk (Risk Profile) | VER10-9494 | Minas / Vivek Yoong |  | Fri 12 Dec 2025 | Mon 22 Dec 2025 | N/A | N/A | 46070 | 46070 | Sprint 37 | Sprint 38 | [12 empty] | 80 | 60 | 5 | Team 3 | 8.5714 | 7.5 | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 11 | bar: SG1 to SG3
Portfolio/Programme Risk (Remaining) |  | Minas / Vivek Yoong |  | Fri 12 Dec 2025 | Mon 22 Dec 2025 | N/A | N/A | 46070 | 46073 | Sprint 38 | Sprint 39 | [12 empty] | 80 | 60 | 5 | Team 3 | 8.5714 | 7.5 | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 11 | bar: SG1 to SG3
Calculators/Cost Models (Chapter 10) |  | Minas / Laurence |  | Thu 18 Dec 2025 | Fri 9 Jan 2025 | N/A | N/A | 46045 | 46045 | Sprint 35 | Sprint 35 | [12 empty] | 20 | 20 | 6 | Team 5 | 2.8571 | 2.5 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 11 | bar: SG1 to SG3
Scenario Analysis (Chapter 7) | VER10-8958 | Minas? (TBC) |  | 46045 | 46050 | 46073 | N/A | 46080 | 46080 | Sprint 39 | Sprint 40 | [12 empty] | 140 | 100 | 5 | Team 3 | 14.2857 | 12.5 | [56 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [21 empty] | 10 | bar: SG1
Star Rates |  | Minas? (TBC) |  | 46059 | 46066 | N/A | 46066 | 46078 | 46080 | Sprint 37 | Sprint 37 | [12 empty] | 90 | 60 |  | Team 2 | 8.5714 | 7.5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 11
TPE (Input Screen) (1) | VER10-9184 | Venkatesh |  | 46069 | 46073 | 46080 | N/A | 46080 | 46080 | Sprint 38 | Sprint 39 | [12 empty] | 350 | 215 | 4 | Team 5 | 30.7143 | 26.875 | [56 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [7 empty] | 20
TPE (Simulation Eng + Worksheet) |  | Venkatesh |  | 46071 | 46073 | 46080 | N/A | 46080 | 46080 | Sprint 38 | Sprint 39
TPE (Schedule/Risk) (3) |  | Venkatesh |  | 46073 | 46073 | 46080 |  | 46080 | 46080 | Sprint 38 | Sprint 39
TPE (Inflation) (6) |  | Venkatesh |  | 46078 | 46078 | 46080 |  | 46085 | 46085 | Sprint 39 | Sprint 39
TPE (Output) (7) |  | Venkatesh |  | 46080 | 46085 | 46087 |  | 46092 | 46092 | Sprint 40 | Sprint 40
TPE (Output) (8) |  | Venkatesh |  | 46080 | 46085 | 46087 |  | 46064 | 46092 | Sprint 41 | Sprint 41
Dashboards (Power BI) |  | Minas |  | 46031 | N/A | N/A | N/A | N/A | N/A | Sprint 39 | Sprint 40 | [12 empty] | 40 | 40 | 2 | Dashboard Team | 5.7143 | 5 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 11 | bar: SG1
Contractor Fee Library | VER10-9271 | Minas |  | 46066 | 46071 | N/A | 46080 | 46108 | 46108 | Sprint 38 | Sprint 38 | [12 empty] | 90 | 80 | 3 | Team 2 | 11.4286 | 10 | [56 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | F | [21 empty] | 10
System Access | VER10-8452 | Minas |  | 46031 | 46038 | N/A | 46045 | 46045 | 46045 | Sprint 35 | Sprint 35 | [12 empty] | 40 | 40 | 3 | Team 5 | 5.7143 | 5 |  |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 20
Audit Log | VER10-8955, VER10-6972 | Minas |  | Done | Done | Done | 46045 | 46051 | 46051 | Sprint 35 | Sprint 35 | [12 empty] | 10 | 11 |  | Team 5 | 1.5714 | 1.375 | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 11 | bar: SG1 to SG7
WBS Tags and Custom Fields | VER10-8916, VER10-8268 | Minas / Manish |  | Done | Done | Done | Done | Done | Done | Sprint 36 | Sprint 36 | [12 empty] | 10 | 10 |  | Team 2 | 1.4286 | 1.25 | [6 empty] | X | F | [6 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 12 | bar: SG1 to SG7
Custom Field Filtering |  | Minas / Manish |  | Done | Done | Done | Done | Done | Done | Sprint 35 | Sprint 35 | [15 empty] | Team 2 | [30 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | bar: SG1 to SG7
Reporting Foundation Admin | VER10-8476 | Minas / Vivek |  | Done | Done | Done | Done | Done | Done | Sprint 36 | Sprint 36 | [12 empty] | 19 | 19 |  | Team 3 | 2.7143 | 2.375 |  |  |  |  | X | X | X | F | [6 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [60 empty] | 14 | bar: SG1 to SG7
Inflation | VER10-8903, VER10-8570 | Minas / Vivek |  | Done | Done | Done | Done | Done | Done | Sprint 37 | Sprint 37 | [12 empty] | 41 | 41 |  | Team 3 | 5.8571 | 5.125 | [10 empty] | X | X | X | X | [14 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [46 empty] | 15 | bar: SG1 to SG6
AR and O&M fixed reports | VER10-7878, VER10-7879 | Minas / Vivek |  | Done | Done | Done | Done | Done | Done | Sprint 38 | Sprint 39 | [12 empty] | 47 | 47 |  | Team 3 | 6.7143 | 5.875 | [7 empty] | X |  |  | X | X | X | X | [28 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 16 | bar: SG1 to SG6
CCESS | VER10-6966 | Minas / Vivek |  | Done | Done | Done | Done | Done | Done | Sprint 37 | Sprint 37 | [12 empty] | 5 | 5 |  | Team 3 | 0.71429 | 0.625 | [42 empty] | X |  |  | X | X | X | X | X |  |  | X | X | X | X | X |  |  | F | [32 empty] | 11 | bar: SG1 to SG4
[24 empty] | 3186 | 2538 | 2623 |  | 362.5714 | 317.25 | 0 | 0 | 0 | 3 | 4 | 4 | 5 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 13 | 20 | 0 | 0 | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 14 | 14 | 14 | 14 | 21 | 0 | 0 | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 14 | 14 | 10 | 10 | 11 | 0 | 0 | 4 | 4 | 4 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457
Key |  | For this week | [24 empty] | Team 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
|  | Complete | [24 empty] | Team 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 5 | 6 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 6 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 1 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109
|  | At risk (Mitigation) | [24 empty] | Team 3 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 5 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 7 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109
|  | Blocked/Late | [24 empty] | Team 4 |  |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 5 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113
[27 empty] | Team 5 |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
Sprint Dates |  | Starts |  | Ends | [22 empty] | Total |  |  | 0 | 0 | 0 | 3 | 4 | 4 | 5 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 9 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 9 | 9 | 9 | 13 | 20 | 0 | 0 | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 14 | 14 | 14 | 14 | 20 | 0 | 0 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 13 | 13 | 9 | 9 | 10 | 0 | 0 | 4 | 4 | 4 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 35 |  | 19/01/26 |  | 02/02/26
Sprint 36 |  | 02/02/26 |  | 16/02/26
Sprint 37 |  | 16/02/26 |  | 02/03/26
Sprint 38 |  | 02/03/26 |  | 16/03/26
Sprint 39 |  | 16/03/26 |  | 27/03/26
Note on D22: Minas Kamel: Richard?

## stage-gates
Gate | Owner | Rationale | Pass Criteria | sheet-col | Carbon Resource Library | Carbon Item Library | Import / Export | IFT - Dynamic Library | IFT - Project Specific Library | Calculators/Cost Models (Chapter 10) | System Access | Audit Log | Custom Field Filtering | --- | WBS Tags and Custom Fields | Reporting Foundation Admin | --- | WBS Carbon & Calc | EPD | Cost to Carbon Library | Auto-Allocate | LTA - Epic 1/2 - RfE + Shell (Entry Point) | LTA - Epic 5 Annual Profiling | Comparator | Carbon Reports | Portfolio/Programme Risk (Risk Profile) | Star Rates | Inflation | CCESS | --- | LTA - Epic 3 - Asset Library | LTA - Epic 4/6 - Data Entry & WBS | Estimate Workflow (Reviewal, Approval, Issuing) | Portfolio/Programme Risk (Remaining) | TPE (Input Screen) (1) | TPE (Simulation Eng + Worksheet) | TPE (Schedule/Risk) (3) | Contractor Fee Library | AR and O&M fixed reports | --- | Scenario Analysis (Chapter 7) | TPE (Inflation) (6) | Dashboards (Power BI) | --- | TPE (Output) (7) | --- | TPE (Output) (8)
SCOPE REFINEMENT
1. Individual PRDs Drafted | Minas | Ensures scope and requirements are explicit before design and build begin, avoiding downstream rework and ambiguity. |  | F | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Thu 18 Dec 2025 | 2026-01-09 | Done | Done |  | Done | Done |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-01-09 | Fri 12 Dec 2025 | 2026-02-06 | Done | Done |  | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-02-16 | 2026-02-18 | 2026-02-20 | 2026-02-13 | Done |  | 2026-01-23 | 2026-02-25 | 2026-01-09 |  | 2026-02-27 |  | 2026-02-27
|  |  | • PRDs drafted for each of the MVP epics | F | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Thu 18 Dec 2025 | 2026-01-09 | Done | Done |  | Done | Done |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-01-09 | Fri 12 Dec 2025 | 2026-02-06 | Done | Done |  | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-02-16 | 2026-02-18 | 2026-02-20 | 2026-02-13 | Done |  | 2026-01-23 | 2026-02-25 | 2026-01-09 |  | 2026-02-27 |  | 2026-02-27
|  |  | • Functional requirements prioritised (Must / Should / Deferred) | F | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Thu 18 Dec 2025 | 2026-01-09 | Done | Done |  | Done | Done |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-01-09 | Fri 12 Dec 2025 | 2026-02-06 | Done | Done |  | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-02-16 | 2026-02-18 | 2026-02-20 | 2026-02-13 | Done |  | 2026-01-23 | 2026-02-25 | 2026-01-09 |  | 2026-02-27 |  | 2026-02-27
|  |  | • In-scope vs out-of-scope clearly defined | F | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Thu 18 Dec 2025 | 2026-01-09 | Done | Done |  | Done | Done |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-01-09 | Fri 12 Dec 2025 | 2026-02-06 | Done | Done |  | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-02-16 | 2026-02-18 | 2026-02-20 | 2026-02-13 | Done |  | 2026-01-23 | 2026-02-25 | 2026-01-09 |  | 2026-02-27 |  | 2026-02-27
|  |  | • Dependencies and assumptions explicitly documented | F | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Thu 18 Dec 2025 | 2026-01-09 | Done | Done |  | Done | Done |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-01-09 | Fri 12 Dec 2025 | 2026-02-06 | Done | Done |  | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-02-16 | 2026-02-18 | 2026-02-20 | 2026-02-13 | Done |  | 2026-01-23 | 2026-02-25 | 2026-01-09 |  | 2026-02-27 |  | 2026-02-27
|  |  | • Dates associated with each of the following Gates are confirmed and committed | F | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Thu 18 Dec 2025 | 2026-01-09 | Done | Done |  | Done | Done |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-01-09 | Fri 12 Dec 2025 | 2026-02-06 | Done | Done |  | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | Fri 12 Dec 2025 | 2026-02-16 | 2026-02-18 | 2026-02-20 | 2026-02-13 | Done |  | 2026-01-23 | 2026-02-25 | 2026-01-09 |  | 2026-02-27 |  | 2026-02-27
2A. PRDs Reviewed & Signed Off (NH) | Richard | Confirms shared understanding and agreement with NH to prevent late scope disputes or rework. | • NH review completed | G | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-23 | 2026-01-23 | Fri 9 Jan 2025 | 2026-01-16 | Done | Done |  | Done | Done |  | 2026-01-09 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-19 | 2026-01-16 | Mon 22 Dec 2025 | 2026-02-13 | Done | Done |  | 2026-01-23 | 2026-01-23 | 2026-01-30 | Mon 22 Dec 2025 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-18 | Done |  | 2026-01-28 | 2026-02-25 | N/A |  | 2026-03-04 |  | 2026-03-04
|  |  | • Explicit NH sign-off received | G | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-23 | 2026-01-23 | Fri 9 Jan 2025 | 2026-01-16 | Done | Done |  | Done | Done |  | 2026-01-09 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-19 | 2026-01-16 | Mon 22 Dec 2025 | 2026-02-13 | Done | Done |  | 2026-01-23 | 2026-01-23 | 2026-01-30 | Mon 22 Dec 2025 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-18 | Done |  | 2026-01-28 | 2026-02-25 | N/A |  | 2026-03-04 |  | 2026-03-04
|  |  | • No open scope alignment questions | G | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-23 | 2026-01-23 | Fri 9 Jan 2025 | 2026-01-16 | Done | Done |  | Done | Done |  | 2026-01-09 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-19 | 2026-01-16 | Mon 22 Dec 2025 | 2026-02-13 | Done | Done |  | 2026-01-23 | 2026-01-23 | 2026-01-30 | Mon 22 Dec 2025 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-18 | Done |  | 2026-01-28 | 2026-02-25 | N/A |  | 2026-03-04 |  | 2026-03-04
|  |  | • Any gaps documented, escalated and resolved | G | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-23 | 2026-01-23 | Fri 9 Jan 2025 | 2026-01-16 | Done | Done |  | Done | Done |  | 2026-01-09 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-19 | 2026-01-16 | Mon 22 Dec 2025 | 2026-02-13 | Done | Done |  | 2026-01-23 | 2026-01-23 | 2026-01-30 | Mon 22 Dec 2025 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-18 | Done |  | 2026-01-28 | 2026-02-25 | N/A |  | 2026-03-04 |  | 2026-03-04
2B - PRD Hand-off to SA | Minas | Ensure that the full scope and implications of the PRD are understood | All questions raised by Vigo/Design and SA are documented and formally resolved. | G | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-23 | 2026-01-23 | Fri 9 Jan 2025 | 2026-01-16 | Done | Done |  | Done | Done |  | 2026-01-09 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-19 | 2026-01-16 | Mon 22 Dec 2025 | 2026-02-13 | Done | Done |  | 2026-01-23 | 2026-01-23 | 2026-01-30 | Mon 22 Dec 2025 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-18 | Done |  | 2026-01-28 | 2026-02-25 | N/A |  | 2026-03-04 |  | 2026-03-04
|  |  | No 'to be clarified' items to remain open unless escalated and approved. | G | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-23 | 2026-01-23 | Fri 9 Jan 2025 | 2026-01-16 | Done | Done |  | Done | Done |  | 2026-01-09 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-19 | 2026-01-16 | Mon 22 Dec 2025 | 2026-02-13 | Done | Done |  | 2026-01-23 | 2026-01-23 | 2026-01-30 | Mon 22 Dec 2025 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-18 | Done |  | 2026-01-28 | 2026-02-25 | N/A |  | 2026-03-04 |  | 2026-03-04
|  |  | Vigo and SA have confirmed in writing that the solution is technically coherent and feasible | G | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-23 | 2026-01-23 | Fri 9 Jan 2025 | 2026-01-16 | Done | Done |  | Done | Done |  | 2026-01-09 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-19 | 2026-01-16 | Mon 22 Dec 2025 | 2026-02-13 | Done | Done |  | 2026-01-23 | 2026-01-23 | 2026-01-30 | Mon 22 Dec 2025 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-18 | Done |  | 2026-01-28 | 2026-02-25 | N/A |  | 2026-03-04 |  | 2026-03-04
|  |  | Confirmation of the timeline | G | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-23 | 2026-01-23 | Fri 9 Jan 2025 | 2026-01-16 | Done | Done |  | Done | Done |  | 2026-01-09 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-19 | 2026-01-16 | Mon 22 Dec 2025 | 2026-02-13 | Done | Done |  | 2026-01-23 | 2026-01-23 | 2026-01-30 | Mon 22 Dec 2025 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-18 | Done |  | 2026-01-28 | 2026-02-25 | N/A |  | 2026-03-04 |  | 2026-03-04
DESIGN STAGES
3. UX/UI Designs Completed | Richard (coordination) | Prevents design churn during development and ensures build teams are working from stable designs. | • UX/UI designs completed for all in-scope MVP flows | H | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-02-11 | 2026-02-20 | N/A | N/A | Done | Done |  | Done | Done |  | 2026-01-30 | 2026-02-11 | 2026-01-24 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2026-02-09 | N/A | N/A | N/A | Done | Done |  | 2026-02-04 | 2026-02-04 | 2026-02-16 | N/A | 2026-02-27 | 2026-02-27 | 2026-02-27 | N/A | Done |  | 2026-02-20 | 2026-02-27 | N/A |  | 2026-03-06 |  | 2026-03-06
|  |  | • Designs reviewed and accepted internally | H | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-02-11 | 2026-02-20 | N/A | N/A | Done | Done |  | Done | Done |  | 2026-01-30 | 2026-02-11 | 2026-01-24 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2026-02-09 | N/A | N/A | N/A | Done | Done |  | 2026-02-04 | 2026-02-04 | 2026-02-16 | N/A | 2026-02-27 | 2026-02-27 | 2026-02-27 | N/A | Done |  | 2026-02-20 | 2026-02-27 | N/A |  | 2026-03-06 |  | 2026-03-06
|  |  | • Ownership agreed (Vigo vs in-house) | H | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-02-11 | 2026-02-20 | N/A | N/A | Done | Done |  | Done | Done |  | 2026-01-30 | 2026-02-11 | 2026-01-24 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2026-02-09 | N/A | N/A | N/A | Done | Done |  | 2026-02-04 | 2026-02-04 | 2026-02-16 | N/A | 2026-02-27 | 2026-02-27 | 2026-02-27 | N/A | Done |  | 2026-02-20 | 2026-02-27 | N/A |  | 2026-03-06 |  | 2026-03-06
|  |  | • No critical design work outstanding for sprint execution | H | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-02-11 | 2026-02-20 | N/A | N/A | Done | Done |  | Done | Done |  | 2026-01-30 | 2026-02-11 | 2026-01-24 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2026-02-09 | N/A | N/A | N/A | Done | Done |  | 2026-02-04 | 2026-02-04 | 2026-02-16 | N/A | 2026-02-27 | 2026-02-27 | 2026-02-27 | N/A | Done |  | 2026-02-20 | 2026-02-27 | N/A |  | 2026-03-06 |  | 2026-03-06
4. Solution Architectures (SAs) Drafted | Richard (coordination) | Grounds delivery commitments in technical reality and surfaces assumptions, risks, and trade-offs early. | • SAs drafted for each epic | I | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-23 | 2026-01-23 | Done |  | Done | Done |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-13 | Done | Done |  | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-02-27 | Done |  | N/A |  | N/A
|  |  | • Architecture simplified to MVP | I | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-23 | 2026-01-23 | Done |  | Done | Done |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-13 | Done | Done |  | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-02-27 | Done |  | N/A |  | N/A
|  |  | • Technical assumptions and risks explicit | I | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-23 | 2026-01-23 | Done |  | Done | Done |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-13 | Done | Done |  | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-02-27 | Done |  | N/A |  | N/A
|  |  | • Key trade-offs documented | I | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-23 | 2026-01-23 | Done |  | Done | Done |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-13 | Done | Done |  | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-02-27 | Done |  | N/A |  | N/A
5. SAs Reviewed & Approved | Jerome | Locks technical feasibility before commitments are made and avoids late architectural rework. | • SAs reviewed and approved | J | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-02-25 | 2026-02-23 | 2026-01-23 | 2026-01-23 | 2026-01-29 | Done |  | Done | Done |  | 2026-02-13 | 2026-02-17 | 2026-02-16 | 2026-02-13 | 2026-02-20 | 2026-02-20 | 2026-02-13 | 2026-02-20 | 2026-02-17 | 2026-02-25 | Done | Done |  | 2026-02-16 | 2026-02-20 | 2026-02-23 | 2026-02-17 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-03-27 | Done |  | 2026-02-27 | 2026-03-04 | N/A |  | 2026-03-11 |  | 2026-02-11
|  |  | • Risks accepted or mitigated | J | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-02-25 | 2026-02-23 | 2026-01-23 | 2026-01-23 | 2026-01-29 | Done |  | Done | Done |  | 2026-02-13 | 2026-02-17 | 2026-02-16 | 2026-02-13 | 2026-02-20 | 2026-02-20 | 2026-02-13 | 2026-02-20 | 2026-02-17 | 2026-02-25 | Done | Done |  | 2026-02-16 | 2026-02-20 | 2026-02-23 | 2026-02-17 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-03-27 | Done |  | 2026-02-27 | 2026-03-04 | N/A |  | 2026-03-11 |  | 2026-02-11
|  |  | • No unresolved feasibility questions | J | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-02-25 | 2026-02-23 | 2026-01-23 | 2026-01-23 | 2026-01-29 | Done |  | Done | Done |  | 2026-02-13 | 2026-02-17 | 2026-02-16 | 2026-02-13 | 2026-02-20 | 2026-02-20 | 2026-02-13 | 2026-02-20 | 2026-02-17 | 2026-02-25 | Done | Done |  | 2026-02-16 | 2026-02-20 | 2026-02-23 | 2026-02-17 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-03-27 | Done |  | 2026-02-27 | 2026-03-04 | N/A |  | 2026-03-11 |  | 2026-02-11
|  |  | • Delivery implications understood by Delivery Manager | J | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-02-25 | 2026-02-23 | 2026-01-23 | 2026-01-23 | 2026-01-29 | Done |  | Done | Done |  | 2026-02-13 | 2026-02-17 | 2026-02-16 | 2026-02-13 | 2026-02-20 | 2026-02-20 | 2026-02-13 | 2026-02-20 | 2026-02-17 | 2026-02-25 | Done | Done |  | 2026-02-16 | 2026-02-20 | 2026-02-23 | 2026-02-17 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-03-27 | Done |  | 2026-02-27 | 2026-03-04 | N/A |  | 2026-03-11 |  | 2026-02-11
|  |  | • All the required Jira tickets have been reviewed and align with the SA The dates committed, as well as assumptions and effort estimate made in Gate 1, remain valid | J | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-02-25 | 2026-02-23 | 2026-01-23 | 2026-01-23 | 2026-01-29 | Done |  | Done | Done |  | 2026-02-13 | 2026-02-17 | 2026-02-16 | 2026-02-13 | 2026-02-20 | 2026-02-20 | 2026-02-13 | 2026-02-20 | 2026-02-17 | 2026-02-25 | Done | Done |  | 2026-02-16 | 2026-02-20 | 2026-02-23 | 2026-02-17 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-03-27 | Done |  | 2026-02-27 | 2026-03-04 | N/A |  | 2026-03-11 |  | 2026-02-11
6. Performance-Aware Design Approved | Yoong | Ensures design and architectural decisions do not inherently introduce performance, scalability, or data-related risk. | • NFR defined (SLOs, throughput, user capacity)